## Sheet1
Meeting | Date of Request | Request | Name of Requestor | Responsible Administrator | Reporting Date & Location | Status
CIT | 2008-12-16 | Keep SMART Boards on Information section of CIT agenda | Dr. Martin | Amy Stewart | March CIT | On-going Remove as of 4/27/09
CIT | 2008-12-16 | Goal #3 / Goal #2 Project: Talbot goals, educational benefits linked to technology | Dr. Martin | Instructional Directors | January CIT February CIT March CIT April CIT | Finance was to ask for a line item in the new budget to fund teacher requests for specific technology. Technology Initiative is awaiting budget approval.
CIT | 2009-01-26 | Middle Level: Compare and contrast BWMS middle level model with proposed model in executive summary utilizing a review of Policy 9190 as a basis. | Dr. Martin | Amanda Hetrick | February Board | Done
CIT | 2009-01-26 | PE: Bring recommended motion for PE to Feb. Board meeting with Executive summary to include a compare and contrast of Option 1, Option 2 and status quo. CIT members that want to provide input should get input to Amanda by Friday, January 30, 2009. | Dr. Martin | Amanda Hetrick | February Board | Done
CIT | 2009-01-26 | WCCC planned instruction: Discuss at February meeting to align with facilities discussion. Discussed at March CIT and passed at April Board. | Dr. Martin | Amanda Hetrick | February CIT March CIT April Board | Done
CIT | 2009-01-26 | Alt Ed: Motion for status quo to February Board. | Dr. Martin | Amanda Hetrick | February Board | Done
CIT | 2009-01-26 | WCCC Consultant: Board feedback and deliverables to Jeff Lockett by Friday, January 30th. Meeting with Jeff Lockett, Jack Martin, Dr. Terrill and Amanda Hetrick to develop report to bring to February Board. WCCC RFI to be revisited at April CIT meeting as Old Business due to a lack of response to RFI. | Dr. Martin | Amanda Hetrick | March CIT April CIT | Not pursuing at this time. Done
CIT | 2009-02-23 | Middle Level: Forward revisions to 9190 Middle Level Course Sequence to Board on second reading | Dr. Martin | Amanda Hetrick | March Board | Done
CIT | 2009-02-23 | Language Arts planned instruction for 6, 7 and 8 should go to Board in the spring with textbook adoption to follow. Textbooks to April CIT. | Dr. Martin | Amanda Hetrick | March Board April CIT | Done. Textbook purchase goes to Finance in May. Board approved.
CIT | 2009-02-23 | Title 1 Program funding for next school year should be discussed at the next CIT meeting and perhaps at the next Finance meeting | Dr. Martin | Rosemarie Green | March CIT March Finance April CIT May CIT | Continued discussion regarding Title and Stimulus.
Policy | 2009-02-24 | Policy 10465 Student Participation and Coaches Needed - corrections | Mrs. Angove | Jack Werner | March Policy | Passed on first reading in April. To May Policy for second reading. Board approved.
Policy | 2009-02-24 | Policy 4020 Annual Operating Budget Development - present and review | Mrs. Angove | Petter Turnquist | March Policy April Policy
Policy | 2009-02-24 | Policy 10510 Discipline Code - modify with principals by adding additional consequences and associated costs. | Mrs. Angove | Amanda Hetrick | March Policy April CIT May CIT | Waiting on information regarding a second tier of Alt. Ed.
Policy | 2009-02-24 | Policy 10930 Behavior Management - to board on first reading with noted revisions | Mrs. Angove | Diane Martin | March Board | Done
Policy | 2009-02-24 | Policy 11301 Visitors to School - to board on first reading with noted revisions | Mrs. Angove | Diane Martin | March Board | Done
Policy | 2009-02-24 | Policy 9301 Special Education Programs - to board on first reading with noted revisions | Mrs. Angove | Diane Martin | March Board | Done
Policy | 2009-02-24 | Policy 7220 Discipline and Corporal Punishment- to board on first reading with noted revisions | Mrs. Angove | Karen Pascale | March Board | Done
Policy | 2009-02-24 | Review policy regarding administration of medication and use of Epi-pen. | Mrs. Angove | Amanda Hetrick | March Policy April Policy | Passed on first reading in April. To May Policy for second reading. Board approved.
Policy | 2009-02-24 | Review policy regarding dual enrollment / credit / weight. To April Policy for second reading. | Mrs. Angove | Amanda Hetrick | March Policy April Policy | On agenda for Special BOD meeting, May 26th to correct typo. Approved but going back to Policy in August.
Policy | 2009-02-24 | Policy 2347 Electronic Information Dissemination- review and bring to May Policy | Mrs. Angove | Karen Pascale | May Policy June Policy | ?
Policy | 2009-02-24 | Review of Records Retention Policy - include language regarding the destruction of meeting tapes. | Mrs. Angove | Amy Stewart | April Policy | Requested to come back by August Policy meeting.
Finance | 2009-02-24 | Staffing model updated | Mr. Lockett | Petter Turnquist | March Finance | Done
Finance | 2009-02-24 | myschoollunch.com executive summary and alternative(s) for next Finance meeting. myschoollunch.com implementation plan and contract for April Finance meeting | Mr. Lockett | Amy Stewart | March Finance April Finance | Done
Finance | 2009-02-24 | Pentamation utilization update | Mr. Lockett | Petter Turnquist | March Finance | Update done. In the process of implementing more modules in FinPlus.
Finance | 2009-02-24 | Transportation software - plan to be presented at next Finance meeting | Mr. Lockett | Brian Collopy | March Finance | Renewed Bus Boss for 1 yr. Online training now, on-site training to come. Evaluating several other programs.
CIT | 2009-03-30 | Read 180 to Finance to be approved as a line item in budget. | Dr. Martin | Diane Martin | March Finance | Waiting on budget approval.
CIT | 2009-03-30 | Evaluation of Middle School Program - list of evaluation criteria for April CIT meeting. | Dr. Martin | Amanda Hetrick | April CIT | Work in progress. Report will be presented at June CIT.
CIT | 2009-03-30 | Administration will provide a report to the Board regarding positive reinforcement regarding performance on standardized tests. | Dr. Martin | Amanda Hetrick |  | Done
CIT | 2009-03-30 | Alt Ed: Discussion in conjunction with discipline updates for April Policy. | Mrs. Angove | Amanda Hetrick | April CIT May CIT
Board | 2009-05-11 | Cell phones as classroom response systems | Mrs. Angove | Hetrick / Stewart | May CIT | Done
Board | 2009-05-11 | Revisit ruling from PDE regarding having a certificated teacher on the receiving end of Distance Learning | Mr. Stewart | Hetrick / Pascale | May CIT | Waiting to hear from solicitor.
Board | 2009-05-11 | Recommendation to alleviate the number of teacher preparations | Dr. Martin | Karen Pascale | May PACCA | ?
Policy | 2009-04-27 | FERPA - Policy 10920 to be brought back to Policy for further discussion | Policy Committee | Hetrick / Stewart | May Policy | Board approved
Policy | 2009-04-27 | Review Policy 3140 - Disciplinary Suspensions | Dr. Martin | Karen Pascale | May Policy
Policy | 2009-04-27 | Review Policy 10100 - Student Attendance | Dr. Martin | Amy Stewart | Future Policy Meeting