## (1) Cap Res.2007.2008
PROJ# | 0502 | 0602 | 0601 | 0401 | 0602, 0508 | 0507, 507R | 0508 | 0508 | 0604 | 0604 | 0609 | 0703 | 0702 | 0704 | 0701 | 0709 | MASTER FACILITIES PLAN | FDK | OTHER | 0705 | 0714 | [10 empty] | 112908.97
ORIG AMT | 87621 | 99010 | 79900 | 698000 | 20316 | 12451.73 | 2430 | 122629 | 13174.5 | 130000 | 5000 | 66200 | 0 | 275000 | 252000 | 79000 | 4385.64 | 34250 | 5940 | 200000 | 235000
ADJUST | -78858.9 | 4407.71 | 1800 | 33695 |  | 6124.25 |  | -3505.2 |  | 2580 | -5000 | 29803.2 |  |  |  |  | 8160.56 | 16925.53 | 12272.68 | 24129.47 |  |  | <--DATABASE | WARREN COUNTY SCHOOL DISTRICT
CONTR DATE | 2005-11-10 | 2006-08-22 | 2006-08-20 | 2004-10-01 | 2006-01-01 | 2006-01-19 | 2006-10-10 | 2006-07-31 | 2006-07-13 |  | 2006-10-18 | 2006-10-30 | 2006-08-30 | 2006-11-20 | 2006-11-20 | 2006-11-20 | 2007-04-19 |  |  | 2007-01-29
DESCRIPTION | AVE EMERG GENERATOR SERVER ROOM KEYSTONE ELECT | EMHS FIRE ALARM NORTHWEST SERVICE CO | BWMS EXTERIOR MASONRY ALLSTATE RESTORATION | WAHS ROOF JMST ROOFING | EMHS SEWAGE TR PLAN, 0602 ALARM SYSTEM 9,318.00 HF LENS. | BWMS, WAHS, EMHS WINDOW REPLACEMENT WTW ARCHITECTS | EMHS SEWAGE TREATMENT PLANT KEYSTONE ELECT | EMHS SEWAGE TREATMENT PLANT WM T SPAEDER CO INC, | SSELC PARK LOT, URBAN ENGINRS OF ERIE , & HRLC | SSELC PARKING LOT, KINGVVIEW ENTERPRISES | SGES VENTILATION SYSTEM, RADON OF ERIE | BWMS, EMHS, SAMHS, WCCC, WAHS, RES, SECURITY SYSTEM UPGRADE HF LENZ | WCCC WELD LAB ADDITION | WAHS & EMHS EXTERNAL ELECT UPGRADE | WCCC & SAMHS FIRE ALARM UPGRADE | SAMHS BLEACHERS | MASTER FACILITIES PLAN Studio Z Architects |  |  | WAHS, YEMS, YAHS, & EMHS TECH ED LAB PROJECT |  |  |  | Capital Reserve Account Activity
[26 empty] | Balances |  | Deposits (+) |  | Checks (-) |  | Running |  | Cash
NET AMOUNT | 8762.1 | 103417.71 | 81700 | 731695 | 20316 | 18575.98 | 2430 | 119123.8 | 13174.5 | 132580 | 0 | 96003.2 | 0 | 275000 | 252000 | 79000 | 12546.2 | 51175.53 | 18212.68 | 224129.47 | 235000 |  |  | Date | Description | Tech | B&G | Tech | B&G | Tech | B&G | Balance |  | Balance | PROJ# | DESCRIPTION
[5 empty] | 2008.06 | [18 empty] | 2004-07-01 |  | -8755.74 | 148027.14 |  |  |  |  | 139271.4 |  | 139271.4
[24 empty] | 2004-07-19 | Deposit-Specs | -8755.74 | 148027.14 |  | 400 |  |  | 139671.4 |  | 139671.4
[24 empty] | 2004-07-26 | Auction-Lander | -8755.74 | 148427.14 |  | 4952.5 |  |  | 144623.9 |  | 144623.9
[24 empty] | 2004-08-13 | Deposit-Specs | -8755.74 | 153379.64 |  | 50 |  |  | 144673.9 |  | 144673.9
[24 empty] | 2004-07-31 | Interest-July | -8755.74 | 153429.64 | 24.05 | 24.06 |  |  | 144722.01 |  | 144722.01
[24 empty] | 2004-08-31 | Interest-August | -8731.69 | 153453.7 | 26.5 | 26.5 |  |  | 144775.01 |  | 144775.01
[24 empty] | 2004-09-08 | Reimbursement | -8705.19 | 153480.2 |  |  | 665.93 | 135995 | 8114.08 |  | 8114.08
[24 empty] | 2004-09-24 | Deposit-Grant | -9371.12 | 17485.2 | 475487 |  |  |  | 483601.08 |  | 483601.08
|  |  |  | -261000 | [19 empty] | 2004-09-24 | Reimbursement | 466115.88 | 17485.2 |  |  |  | 76875 | 406726.08 |  | 406726.08
[24 empty] | 2004-09-30 | Interest-Sept | 466115.88 | -59389.8 | 15.59 | 15.59 |  |  | 406757.26 |  | 406757.26
[24 empty] | 2004-10-26 | Reimbursement | 466131.47 | -59374.21 |  |  |  | 545.6 | 406211.66 |  | 406211.66
[24 empty] | 2004-10-26 | Transfer | 466131.47 | -59919.81 |  | 250000 |  |  | 656211.66 |  | 656211.66
[24 empty] | 2004-10-31 | Interest-Oct | 466131.47 | 190080.19 | 71.8 | 71.8 |  |  | 656355.26 |  | 656355.26
[24 empty] | 2004-11-30 | Interest-Nov | 466203.27 | 190151.99 | 120.22 | 120.22 |  |  | 656595.7 |  | 656595.7
[24 empty] | 2004-12-21 | Reimbursement | 466323.49 | 190272.21 |  |  |  | 430.88 | 656164.82 |  | 656164.82
[24 empty] | 2004-12-31 | Interest-Dec | 466323.49 | 189841.33 | 116.48 | 116.48 |  |  | 656397.78 |  | 656397.78
[24 empty] | 2005-01-18 | Sprint-E Rate | 466439.97 | 189957.81 | 7257.6 |  |  |  | 663655.38 |  | 663655.38
[24 empty] | 2005-01-20 | Verizon-E Rate | 473697.57 | 189957.81 | 111534.41 |  |  |  | 775189.79 |  | 775189.79
[24 empty] | 2005-02-01 | Deposit-Specs | 585231.98 | 189957.81 |  | 250 |  |  | 775439.79 |  | 775439.79
[24 empty] | 2005-02-08 | Interest-Jan | 585231.98 | 190207.81 | 130.83 | 130.83 |  |  | 775701.45 |  | 775701.45
[24 empty] | 2005-02-16 | Reimbursement | 585362.81 | 190338.64 |  |  |  | 48130 | 727571.45 |  | 727571.45
[24 empty] | 2005-02-23 | Tower Eng-Refund | 585362.81 | 142208.64 | 101.52 |  |  |  | 727672.97 |  | 727672.97
[24 empty] | 2005-03-09 | Interest-Feb | 585464.33 | 142208.64 | 129.74 | 129.74 |  |  | 727932.45 |  | 727932.45
[24 empty] | 2005-03-23 | Reimbursement | 585594.07 | 142338.38 |  |  | 2250 |  | 725682.45 |  | 725682.45
[24 empty] | 2005-04-07 | Dobson-E Rate | 583344.07 | 142338.38 | 5273.57 |  |  |  | 730956.02 |  | 730956.02
[24 empty] | 2005-04-11 | Gateway | 588617.64 | 142338.38 |  |  | 14087 |  | 716869.02 |  | 716869.02
[24 empty] | 2005-04-11 | Interest-March | 574530.64 | 142338.38 | 138.67 | 138.67 |  |  | 717146.36 |  | 717146.36
[24 empty] | 2005-04-14 | Reimbursement | 574669.31 | 142477.05 |  |  | 4852.68 |  | 712293.68 |  | 712293.68
[24 empty] | 2005-04-28 | Reimbursement | 569816.63 | 142477.05 |  |  | 555.6 |  | 711738.08 |  | 711738.08
[24 empty] | 2005-05-04 | AT & T - E Rate | 569261.03 | 142477.05 | 351.86 |  |  |  | 712089.94 |  | 712089.94
[24 empty] | 2005-05-13 | Interest-April | 569612.89 | 142477.05 | 135.56 | 135.56 |  |  | 712361.06 |  | 712361.06
[24 empty] | 2005-05-25 | Reimbursement | 569748.45 | 142612.61 |  |  | 49.28 |  | 712311.78 |  | 712311.78
[24 empty] | 2005-06-27 | Interest-May | 569699.17 | 142612.61 | 149.56 | 149.56 |  |  | 712610.9 |  | 712610.9
[24 empty] | 2005-06-27 | Reimbursement | 569848.73 | 142762.17 |  |  | 175 |  | 712435.9 |  | 712435.9
[24 empty] | 2005-06-30 | Interest - June | 569673.73 | 142762.17 | 140.28 | 140.27 |  |  | 712716.45 |  | 712716.45
[24 empty] | 2005-06-30 | Audited Balance | 569814.01 | 142902.44 | 87.2 | 87.2 |  | 9.4 | 712881.45 |  | 712881.45
[24 empty] | 2005-06-30 | Audit adjustment net due from Gen Fund | 569901.21 | 142980.24 |  | 265188.55 |  |  | 978070 | <--AGREES TO AUDIT
[24 empty] | 2005-07-19 | Deposit-N. Warren | 569901.21 | 408168.79 |  | 7000 |  |  | 985070 |  | 985070
[24 empty] | 2005-07-22 | CD-National Cty | 569901.21 | 415168.79 |  |  |  |  | 985070 |  | 985070
[24 empty] | 2005-07-31 | Interest - July | 569901.21 | 415168.79 | 297.25 | 297.26 |  |  | 985664.51
[24 empty] | 2005-08-31 | Interest - August | 570198.46 | 415466.05 | 530.07 | 530.08 |  |  | 986724.66 |  | 986724.66
[24 empty] | 2005-08-18 | Emerald Data | 570728.53 | 415996.13 |  |  | 175 |  | 986549.66 |  | 986549.66
[24 empty] | 2005-08-18 | Emerald Data | 570553.53 | 415996.13 |  |  | 17.5 |  | 986532.16 |  | 986532.16 | August TR
|  |  |  | -108315 | [19 empty] | 2005-08-29 | Jamestown Roofing | 570536.03 | 415996.13 |  |  |  | 108315 | 878217.16 |  | 878217.16
[24 empty] | 2005-09-07 | Tower Engineer | 570536.03 | 307681.13 |  |  |  | 143.51 | 878073.65 |  | 878073.65
|  |  |  | -259335 | [19 empty] | 2005-09-07 | Jamestown Roofing | 570536.03 | 307537.62 |  |  |  | 259335 | 618738.65 |  | 618738.65
[24 empty] | 2005-09-07 | ASCC Inc. | 570536.03 | 48202.62 |  |  | 42504 |  | 576234.65 |  | 576234.65
[24 empty] | 2005-09-30 | Interest - Sep | 528032.03 | 48202.62 | 697.7 | 697.71 |  |  | 577630.06 |  | 577630.06
[24 empty] | 2005-09-12 | Gen Fund TRF | 528729.73 | 48900.33 |  | 250000 |  |  | 827630.06 |  | 827630.06
[24 empty] | 2005-10-11 | House Purch - SSElC | 528729.73 | 298900.33 |  |  |  | 1000 | 826630.06 |  | 826630.06
[24 empty] | 2005-10-20 | House Purch - SSElC | 528729.73 | 297900.33 |  |  |  | 25000 | 801630.06 |  | 801630.06
[24 empty] | 2005-10-31 | Interest - October | 528729.73 | 272900.33 | 1039.29 | 1039.29 |  |  | 803708.64 |  | 803708.64
[24 empty] | 2005-11-22 | Gen Fund TRF | 529769.02 | 273939.62 |  | 1000000 |  |  | 1803708.64 |  | 1803708.64
[24 empty] | 2005-11-30 | Interest - Nov | 529769.02 | 1273939.62 | 1294.06 | 1294.07 |  |  | 1806296.77 |  | 1806296.77
[24 empty] | 2005-10-20 | CD Interest | 531063.08 | 1275233.69 | 1256.25 | 1256.25 |  |  | 1808809.27 |  | 1808809.27
[24 empty] | 2005-12-06 | E-RATE (AT&T) | 532319.33 | 1276489.94 | 575.04 |  |  |  | 1809384.31 |  | 1809384.31
[24 empty] | 2005-12-20 | Bid Fees | 532894.37 | 1276489.94 |  | 325 |  |  | 1809709.31 |  | 1809709.31
[24 empty] | 2005-12-31 | Interest - Dec | 532894.37 | 1276814.94 | 1968.79 | 1968.79 |  |  | 1813646.89 |  | 1813646.89
[24 empty] | 2006-01-12 | WTW Architects | 534863.16 | 1278783.73 |  |  |  | 4064.56 | 1809582.33 |  | 1809582.33
[24 empty] | 2006-01-31 | Interest - Jan | 534863.16 | 1274719.17 | 2292.22 | 2292.23 |  |  | 1814166.78 |  | 1814166.78
[24 empty] | 2006-02-28 | E-RATE | 537155.38 | 1277011.4 | 158872.58 |  |  |  | 1973039.36 |  | 1973039.36
[24 empty] | 2006-02-28 | Interest - Feb | 696027.96 | 1277011.4 | 2042.5 | 2042.5 |  |  | 1977124.36 |  | 1977124.36
[24 empty] | 2006-03-31 | Interest - Mar | 698070.46 | 1279053.9 | 2481.99 | 2482 |  |  | 1982088.35 |  | 1982088.35
[5 empty] | -12527.2 | [18 empty] | 2006-04-10 | HF Lenz | 700552.45 | 1281535.9 |  |  |  | 12527.2 | 1969561.15
[24 empty] | 2006-04-30 | Interest - Apr | 700552.45 | 1269008.7 | 2283.22 | 2283.23 |  |  | 1974127.6
[24 empty] | 2006-05-01 | WTW Architects | 702835.67 | 1271291.93 |  |  |  | 12166.56 | 1961961.04 |  |  |  | 30427.02
[5 empty] | -5733.26 | [18 empty] | 2006-05-03 | HF Lenz | 702835.67 | 1259125.37 |  |  |  | 5733.26 | 1956227.78
[24 empty] | 2006-05-31 | Interest - May | 702835.67 | 1253392.11 | 2722.36 | 2722.37 |  |  | 1961672.51
[24 empty] | 2006-06-23 | Deposit | 705558.03 | 1256114.48 |  | 700 |  |  | 1962372.51
[24 empty] | 2006-06-30 | Interest - June | 705558.03 | 1256814.48 | 2501.33 | 2501.33 |  |  | 1967375.17 |  | 1967375.17
[24 empty] | 2006-06-30 | Audit adjustment net due from Gen Fund | 708059.36 | 1259315.81 |  | 203053.23 |  |  | 2170428.4 | <--AGREES TO AUDIT
[24 empty] | 2006-07-11 | Deposit | 708059.36 | 1462369.04 | 245.6 |  |  |  | 2170674 |  | 2170674
|  |  |  | -25650 | [19 empty] | 2006-07-13 | Jamestown Roofing | 708304.96 | 1462369.04 |  |  |  | 25650 | 2145024 | J | 2145024 |  | WAHS ROOF REPLACEMENT
[9 empty] | -4074.5 | [14 empty] | 2006-07-27 | Urban Engineers | 708304.96 | 1436719.04 |  |  |  | 4074.5 | 2140949.5 |  | 2140949.5 |  | SSELC PARKING LOT
[24 empty] | 2006-07-31 | Interest - July | 708304.96 | 1432644.54 | 2616.3 | 2616.3 |  |  | 2146182.1 |  | 2146182.1
[24 empty] | 2006-08-03 | Deposit | 710921.26 | 1435260.84 |  | 112.45 |  |  | 2146294.55 |  | 2146294.55 |  | SCRAP METAL
[24 empty] | 2006-08-03 | Deposit ACT 183 Grant | 710921.26 | 1435373.29 | 200000 |  |  |  | 2346294.55 |  | 2346294.55
[8 empty] | -26759.7 | [15 empty] | 2006-08-08 | WillIam Spaeder | 910921.26 | 1435373.29 |  |  |  | 26759.7 | 2319534.85 | J | 2319534.85 |  | EMHS SEWAGE TREATMENT
|  | -42944.97 | [21 empty] | 2006-08-08 | Northwest Service CO | 910921.26 | 1408613.59 |  |  |  | 42944.97 | 2276589.88 | J | 2276589.88 |  | EHMS FIRE ALARM SYSTEM
[8 empty] | -4851 | [15 empty] | 2006-08-22 | WillIam Spaeder | 910921.26 | 1365668.62 |  |  |  | 4851 | 2271738.88 | J | 2271738.88 |  | EMHS SEWAGE TREATMENT
[24 empty] | 2006-08-31 | Interest -August | 910921.26 | 1360817.62 | 2673.22 | 2673.22 |  |  | 2277085.32 |  | 2277085.32
[5 empty] | -2497.7 | [18 empty] | 2006-09-06 | HF Lenz | 913594.48 | 1363490.84 |  |  |  | 2497.7 | 2274587.62 | J | 2274587.62 |  | EMHS SEWAGE TREATMENT $1100,EMHS FIRE ALARM $1397.70
|  | -47586.35 | [21 empty] | 2006-09-11 | Northwest Service CO | 913594.48 | 1360993.14 |  |  |  | 47586.35 | 2227001.27 |  | 2227001.27 |  | EHMS FIRE ALARM SYSTEM
|  |  | -61251 | [20 empty] | 2006-09-19 | All State Restoration | 913594.48 | 1313406.79 |  |  |  | 61251 | 2165750.27 |  | 2165750.27 |  | BWMS EXTERIOR MASONARY WORK
|  |  | -15649 | [20 empty] | 2006-09-26 | All State Restoration | 913594.48 | 1252155.79 |  |  |  | 15649 | 2150101.27 |  | 2150101.27 |  | BWMS EXTERIOR MASONARY WORK
[10 empty] | -117000 | [13 empty] | 2006-09-26 | Kingsview Enterprises | 913594.48 | 1236506.79 |  |  |  | 117000 | 2033101.27 |  | 2033101.27 |  | SOUTH STREET PAVING PARKING LOT
[24 empty] | 2006-09-30 | Interest -September | 913594.48 | 1119506.79 | 2399.795 | 2399.795 |  |  | 2037900.86 |  | 2037900.86
|  |  |  | -35350 | [19 empty] | 2006-10-03 | Jamestown Roofing | 915994.275 | 1121906.585 |  |  |  | 35350 | 2002550.86 |  | 2002550.86 |  | WAHS ROOF REPLACEMENT
[5 empty] | -1565.9 | [18 empty] | 2006-10-10 | HF Lenz | 915994.275 | 1086556.585 |  |  |  | 1565.9 | 2000984.96 |  | 2000984.96 |  | EMHS FIRE ALARM SYSTEM
[6 empty] | -12451.73 | [17 empty] | 2006-10-10 | WTW Architects | 915994.275 | 1084990.685 |  |  |  | 12451.73 | 1988533.23 |  | 1988533.23 |  | WINDOW REPLACEMENTBWMS,WAHS, EMHS
[7 empty] | -2187 | [16 empty] | 2006-10-18 | Keystone ElectrIc | 915994.275 | 1072538.955 |  |  |  | 2187 | 1986346.23 |  | 1986346.23 |  | EMHS SEWAGE TREATMENT PLANT
[24 empty] | 2006-10-25 | 2006-2007 GF Budget Allocation | 915994.275 | 1070351.955 |  | 1250000 |  |  | 3236346.23 | in june | 3236346.23
[24 empty] | 2006-10-31 | West PA Net Inc, | 915994.275 | 2320351.955 |  |  | 500000 |  | 2736346.23 |  | 2736346.23 |  | BROADBAND
[24 empty] | 2006-10-31 | Interest -October | 415994.275 | 2320351.955 | 2300.735 | 2030.725 |  |  | 2740677.69 |  | 2740677.69 |  | ORIGINALLY 4061.47/2
[7 empty] | -243 | [16 empty] | 2006-11-29 | Keystone Electric | 418295.01 | 2322382.68 |  |  |  | 243 | 2740434.69 |  | 2740434.69 | .0508.3 | EMSH SEWAGE TREATMENT
[6 empty] | -6124.25 | [17 empty] | 2006-11-29 | WTW Architects | 418295.01 | 2322139.68 |  |  |  | 6124.25 | 2734310.44 |  | 2734310.44 | .0507r | WINDOW REPLACEMENTREDESIGN
[24 empty] | 2006-11-30 | Interest -November | 418295.01 | 2316015.43 | 2134.02 | 2134.02 |  |  | 2738578.48 |  | 2738578.48
[24 empty] | 2006-12-01 | ERATE | 420429.03 | 2318149.45 | 590.39 |  |  |  | 2739168.87 |  | 2739168.87 |  | AT&T
|  | -12886.39 | [21 empty] | 2006-12-07 | Northwest Service CO | 421019.42 | 2318149.45 |  |  |  | 12886.39 | 2726282.48 |  | 2726282.48 | .0602.4 | EMHS FIRE ALARM SYSTEM REPLACEMENT FINAL PAYMENT
| -8762.1 | [22 empty] | 2006-12-18 | Keystone Electric | 421019.42 | 2305263.06 |  |  | 8762.1 |  | 2717520.38 |  | 2717520.38 | .0502.4 | EMERGENCY GENERATOR ALL VALLEY SERVER ROOM FINAL PYMT
[8 empty] | -87513.1 | [15 empty] | 2006-12-20 | Wm T Spaeder Co, Inc. | 412257.32 | 2305263.06 |  |  |  | 87513.1 | 2630007.28 |  | 2630007.28 | .0508.3 | EMSH SEWAGE TREATMENT PLANT IMPROVEMENTS FINAL PAYMENT
[10 empty] | -15580 | [13 empty] | 2006-12-20 | Kingsview Enterprises | 412257.32 | 2217749.96 |  |  |  | 15580 | 2614427.28 |  | 2614427.28 | .0604.1 | SSELC PARK LOT PAVING FINAL PAYMENT
[24 empty] | 2006-12-31 | Interest -December | 412257.32 | 2202169.96 | 2057.53 | 2057.53 |  |  | 2618542.34 |  | 2618542.34
[24 empty] | 2007-01-24 | ERATE | 414314.85 | 2204227.49 | 48785.2 |  |  |  | 2667327.54 |  | 2667327.54 |  | VERIZON
[24 empty] | 2007-01-24 | ERATE | 463100.05 | 2204227.49 | 6835.94 |  |  |  | 2674163.48 |  | 2674163.48 |  | DOBSON
[24 empty] | 2007-01-31 | Interest - January | 469935.99 | 2204227.49 | 2179 | 2179 |  |  | 2678521.48 |  | 2678521.48
[15 empty] | -3646.33 | [8 empty] | 2007-02-02 | HF Lenz | 472114.99 | 2206406.49 |  |  |  | 3646.33 | 2674875.15 |  |  | 0.0701 | FIRE ALARM UPGRADES
[15 empty] | -11624 | [8 empty] | 2007-02-02 | HF Lenz | 472114.99 | 2202760.16 |  |  |  | 11624 | 2663251.15 |  | 2663251.15 | 0.0701 | FINAL WCCC & SAMS FIRE Alarm Upgrades, ENGINEERING SERVICES
[24 empty] | 2007-02-28 | Interest - February | 472114.99 | 2191136.16 | 52.79 | 52.79 |  |  | 2663356.73 |  | 2663356.73 |  | 1951.945 | ESTIMATE FOR BANK ERROR
[24 empty] | 2007-03-12 | SCRAP METAL | 472167.78 | 2191188.95 |  | 661.2 |  |  | 2664017.93
[24 empty] | 2007-03-16 | Bid Fees | 472167.78 | 2191850.15 |  | 1300 |  |  | 2665317.93 |  | 2665317.93 |  | 13,000 VS 1300
[24 empty] | 2007-03-16 | ERATE | 472167.78 | 2193150.15 | 6288.44 |  |  |  | 2671606.37 |  | 2671606.37 |  | ONE COMMUNICATIONS
[9 empty] | -4500 | [14 empty] | 2007-03-22 | HRLC ARCHTECTS (604) | 478456.22 | 2193150.15 |  |  |  | 4500 | 2667106.37 |  | 2667106.37 | 0.0604 | FINAL SSELC PARKING LOT
|  |  | -4800 | [20 empty] | 2007-03-22 | HRLC ARCHTECTS (601) | 478456.22 | 2188650.15 |  |  |  | 4800 | 2662306.37 |  | 2662306.37 | 0.0601 | BWMS EXTERIOR MANONRY REPOINTING
[15 empty] | -4907.2 | [8 empty] | 2007-03-22 | HF Lenz (701) | 478456.22 | 2183850.15 |  |  |  | 4907.2 | 2657399.17 |  | 2657399.17 | 0.0701 | WCCC & SAMHS FIRE ALARM UPGRADES
[12 empty] | -1422.47 | [11 empty] | 2007-03-22 | HF Lenz (703) | 478456.22 | 2178942.95 |  |  |  | 1422.47 | 2655976.7 |  | 2655976.7 | 0.0703 | SECURITY SYS UPGRADES 6 SCHOOLS
[14 empty] | -6150 | [9 empty] | 2007-03-22 | HF Lenz (704) | 478456.22 | 2177520.48 |  |  |  | 6150 | 2649826.7 |  | 2649826.7 | 0.0704 | EXTERIOR ELECT UPGRADES
[24 empty] | 2007-03-31 | Interest - March | 478456.22 | 2171370.48 | 3945.61 | 3945.61 |  |  | 2657717.92 |  | 2657717.92 |  | 3969.175
[17 empty] | -4385.64 | [6 empty] | 2007-04-19 | Studio Z Architects (MFP) | 482401.83 | 2175316.09 |  |  |  | 4385.64 | 2653332.28 |  | 2653332.28 |  | Facilities Master Plan
[24 empty] | 2007-04-30 | Interest - April | 482401.83 | 2170930.45 | 2332.46 | 2332.46 |  |  | 2657997.2
[14 empty] | -181.87 | [9 empty] | 2007-05-10 | Prints & More by Holy (0704) | 484734.29 | 2173262.91 |  |  |  | 181.87 | 2657815.33
[24 empty] | 2007-05-24 | SCRAP METAL | 484734.29 | 2173081.04 |  | 63 |  |  | 2657878.33
[24 empty] | 2007-05-31 | Interest - May | 484734.29 | 2173144.04 | 2331.025 | 2331.025 |  |  | 2662540.38
[24 empty] | 2007-06-18 | Bid Fees | 487065.315 | 2175475.065 |  | 1800 |  |  | 2664340.38
[17 empty] | -4265.11 | [6 empty] | 2007-06-14 | Studio Z Architects (MFP) | 487065.315 | 2177275.065 |  |  |  | 4265.11 | 2660075.27
[14 empty] | -17274.83 | [9 empty] | 2007-06-19 | Northwest Service CO (0704) | 487065.315 | 2173009.955 |  |  |  | 17274.83 | 2642800.44
[16 empty] | -79000 | [7 empty] | 2007-06-22 | Sheffield Township Spvrs (0709) | 487065.315 | 2155735.125 |  |  |  | 79000 | 2563800.44
[24 empty] | 2007-06-30 | Interest - June | 487065.315 | 2076735.125 | 4318.83 | 4318.83 |  |  | 2572438.1
[14 empty] | -230 | [9 empty] | 2007-07-10 | H.F. Lenz (0704) EMHS | 491384.145 | 2081053.955 |  |  |  | 230 | 2572208.1 |  |  | 0704 | EMHS ELECTRICAL UPGRADES
[14 empty] | -4315.38 | [9 empty] | 2007-07-11 | H.F. Lenz (0704) WAHS | 491384.145 | 2080823.955 |  |  |  | 4315.38 | 2567892.72 |  |  | 0704 | WCSD ELECTRICAL UPGRADES
[14 empty] | -2066.4 | [9 empty] | 2007-07-11 | H.F. Lenz (0704) WCCC/ SAMHS | 491384.145 | 2076508.575 |  |  |  | 2066.4 | 2565826.32 |  |  | 0704 | WCSD ELECTRICAL UPGRADES
[12 empty] | -633 | [11 empty] | 2007-07-11 | H.F. Lenz (0703) SECURITY SYS | 491384.145 | 2074442.175 |  |  |  | 633 | 2565193.32 |  |  | 0703 | WCSD SECURITY UPGRADES
[17 empty] | -1845.15 | [6 empty] | 2007-07-11 | Studio Z Architects (MFP) | 491384.145 | 2073809.175 |  |  |  | 1845.15 | 2563348.17
[24 empty] | 2007-07-13 | Segal & Son Scrap Metal | 491384.145 | 2071964.025 |  | 144 |  |  | 2563492.17 |  |  |  | SCRAP METAL
[24 empty] | 2007-07-17 | Northwest Service CO (0704) | 491384.145 | 2072108.025 |  |  |  | 51353.05 | 2512139.12 |  |  | 0704 | WCSD ELECTRICAL UPGRADES
[24 empty] | 2007-07-31 | Segal & Son Scrap Metal | 491384.145 | 2020754.975 |  | 89.6 |  |  | 2512228.72 |  |  |  | SCRAP METAL
[24 empty] | 2007-07-31 | Interest - July | 491384.145 | 2020844.575 | 4913.635 | 4913.635 |  |  | 2522055.99 |  |  |  | INTEREST | 4913.635
[24 empty] | 2007-08-02 | RE MICHAEL | 496297.78 | 2025758.21 |  |  | 1515.53 |  | 2520540.46 |  |  | TECH | FDK CONDENSING UNITS LAB
[17 empty] | -1845.15 | [6 empty] | 2007-08-07 | Studio Z Architects (MFP) | 494782.25 | 2025758.21 |  |  |  | 1845.15 | 2518695.31 |  |  | MFP
[15 empty] | -2572.33 | [8 empty] | 2007-08-10 | H.F. Lenz (0701) WCCC SAMHS | 494782.25 | 2023913.06 |  |  |  | 2572.33 | 2516122.98 |  |  | 0701 | WCCC SAMHS FIRE ALARM UPGRADES
[14 empty] | -97649.04 | [9 empty] | 2007-08-10 | Northwest Service CO (0704) | 494782.25 | 2021340.73 |  |  |  | 97649.04 | 2418473.94 |  |  | 0704 | EXTERIOR ELECTRICAL UPGRADES
[20 empty] | -611 |  |  |  | 2007-08-10 | Bickmire Trucking Co (0705) | 494782.25 | 1923691.69 |  |  |  | 611 | 2417862.94 |  |  | 0705 | TECH ED LAB
[15 empty] | -74128 | [8 empty] | 2007-08-15 | Life Safety (0701.4) | 494782.25 | 1923080.69 |  |  |  | 74128 | 2343734.94 |  |  | 0701 | FIRE ALARM UPGRADES
[18 empty] | -10040 | [5 empty] | 2007-08-21 | Hewlett Packard Company | 494782.25 | 1848952.69 |  |  | 10040 |  | 2333694.94 |  |  | TECH | FDK SOFTWARE, BUSINESS LICENSES, TECH EQUIP
[18 empty] | -3280 | [5 empty] | 2007-08-21 | Government Connection | 484742.25 | 1848952.69 |  |  | 3280 |  | 2330414.94 |  |  | TECH | FDK ECHNOLOGY EQUIP
[18 empty] | -2090 | [5 empty] | 2007-08-21 | Lancaster Lebanon IU 13 | 481462.25 | 1848952.69 |  |  | 2090 |  | 2328324.94 |  |  | TECH | FDK SOFTWARE, BUSINESS LICENSES, TECH EQUIP
[24 empty] | 2007-08-23 | Segal & Son Scrap Metal | 479372.25 | 1848952.69 |  | 278 |  |  | 2328602.94
[14 empty] | -21215.96 | [9 empty] | 2007-08-27 | Northwest Service CO (0704) | 479372.25 | 1849230.69 |  |  |  | 21215.96 | 2307386.98
[24 empty] | 2007-08-30 | Segal & Son Scrap Metal | 479372.25 | 1828014.73 |  | 58.75 |  |  | 2307445.73
[24 empty] | 2007-08-31 | Interest - August | 479372.25 | 1828073.48 | 4569.65 | 4569.65 |  |  | 2316585.03
[12 empty] | -564.73 | [11 empty] | 2007-09-10 | HF Lens Company (0703) | 483941.9 | 1832643.13 |  |  |  | 564.73 | 2316020.3 |  |  | 0703 | ENGINEERING TECH
[20 empty] | -13455 |  |  |  | 2007-09-10 | Rabe Environmental Sys (0705) | 483941.9 | 1832078.4 |  |  |  | 13455 | 2302565.3 |  |  | 0705 | TECH ED LAB
[20 empty] | -85.5 |  |  |  | 2007-09-10 | Birkmire Trucking (0705) | 483941.9 | 1818623.4 |  |  |  | 85.5 | 2302479.8 |  |  | 0705 | TECH ED LAB, shipping
[17 empty] | -205.15 | [6 empty] | 2007-09-10 | Paul Zipple, RA LLC | 483941.9 | 1818537.9 |  |  |  | 205.15 | 2302274.65 |  |  | MFP | MASTER FACILITIES PLAN
[15 empty] | -75756 | [8 empty] | 2007-09-18 | Life Safety (0701.4) | 483941.9 | 1818332.75 |  |  |  | 75756 | 2226518.65 |  |  | 0701 | FIRE ALARM UPGRADES
[20 empty] | -85.5 |  |  |  | 2007-09-21 | Bickmire Trucking Co (0705) | 483941.9 | 1742576.75 |  |  |  | 85.5 | 2226433.15 |  |  | 0705 | TECH ED LAB
[20 empty] | -76617.9 |  |  |  | 2007-09-21 | Keystone Electric (0705.2) | 483941.9 | 1742491.25 |  |  |  | 76617.9 | 2149815.25 |  |  | 0705 | TECH ED LAB
[20 empty] | -20119.5 |  |  |  | 2007-09-21 | Rabe Environmental Sys (0705) | 483941.9 | 1665873.35 |  |  |  | 20119.5 | 2129695.75 |  |  | 0705 | TECH ED LAB
[24 empty] | 2007-09-30 | Interest-Sept | 483941.9 | 1645753.85 | 3841.635 | 3841.635 |  |  | 2137379.02
[14 empty] | -12968.05 | [9 empty] | 2007-10-02 | Northwest Service Company (0704.4) | 487783.535 | 1649595.485 |  |  |  | 12968.05 | 2124410.97 |  |  | 0704 | EXTERIOR ELECTRICAL UPGRADES
[24 empty] | 2007-10-02 | Segal & Son Scrap Metal | 487783.535 | 1636627.435 |  | 137.5 |  |  | 2124548.47
|  |  |  | -42045 | [19 empty] | 2007-10-09 | Hallgren, Restifo, Loop & Coughlin (0301.03) | 487783.535 | 1636764.935 |  |  |  | 42045 | 2082503.47 |  |  | 0401 | WAHS ROOF REPLACEMENT
[19 empty] | -5500 |  |  |  |  | 2007-10-09 | Daniel Dancu, IDA, LLC | 487783.535 | 1594719.935 |  |  |  | 5500 | 2077003.47 |  |  |  | FDK ENROLLMENT PROJECTIONS TOWSEY
[20 empty] | -171 |  |  |  | 2007-10-12 | Bickmire Trucking Co (0705) | 487783.535 | 1589219.935 |  |  |  | 171 | 2076832.47 |  |  | 0705 | TECH ED LAB
[19 empty] | -440 |  |  |  |  | 2007-10-22 | James P. Hunter PE, PLS | 487783.535 | 1589048.935 |  |  |  | 440 | 2076392.47 |  |  |  | BWMS DEED RESEARCH
[20 empty] | -85 |  |  |  | 2007-10-22 | Bickmire Trucking Co (0705) | 487783.535 | 1588608.935 |  |  |  | 85 | 2076307.47 |  |  | 0705 | TECH ED LAB
[24 empty] | 2007-10-25 | ERATE | 487783.535 | 1588523.935 | 310000 |  |  |  | 2386307.47 |  |  |  | ERATE DEPOSIT
[20 empty] | -19611 |  |  |  | 2007-10-29 | Rabe Environmental Sys (0705) | 797783.535 | 1588523.935 |  |  |  | 19611 | 2366696.47 |  |  | 0705 | TECH ED LAB
[14 empty] | -12161 | [9 empty] | 2007-10-29 | H.F. Lenz | 797783.535 | 1568912.935 |  |  |  | 12161 | 2354535.47 |  |  | 0704 | EXT. ELECTRICAL UPGRADES
[20 empty] | -21483 |  |  |  | 2007-10-29 | Keystone Electric | 797783.535 | 1556751.935 |  |  |  | 21483 | 2333052.47 |  |  | 0705 | TECH ED LAB
[24 empty] | 2007-10-31 | October Interest | 797783.535 | 1535268.935 | 3974.13 | 3974.13 |  |  | 2341000.73
[20 empty] | -3435.07 |  |  |  | 2007-11-05 | Innovative Construction & Mechanical LLC | 801757.665 | 1539243.065 |  |  |  | 3435.07 | 2337565.66 |  |  | 0705 | TECH ED LAB
[20 empty] | -46149.75 |  |  |  | 2007-11-05 | Innovative Construction & Mechanical LLC | 801757.665 | 1535807.995 |  |  |  | 46149.75 | 2291415.91 |  |  | 0705 | TECH ED LAB
[19 empty] | -3646.95 |  |  |  |  | 2007-11-05 | Gov Connection | 801757.665 | 1489658.245 |  |  | 3646.95 |  | 2287768.96 |  |  |  | SUPPLIES (CREDIT CARD)
[14 empty] | -2180.75 | [9 empty] | 2007-11-08 | H.F. Lenz | 798110.715 | 1489658.245 |  |  |  | 2180.75 | 2285588.21 |  |  | 0704 | EXT. ELECTRICAL UPGRADES
[24 empty] | 2007-11-30 | Segal & Son Scrap Metal | 798110.715 | 1487477.495 |  | 44.1 |  |  | 2285632.31
[24 empty] | 2008-11-30 | Interest-Nov | 798110.715 | 1487521.595 | 3921.05 | 3921.05 |  |  | 2293474.41
[12 empty] | -316 | [11 empty] | 2007-12-03 | H.F. Lenz | 802031.765 | 1491442.645 |  |  |  | 316 | 2293158.41 |  |  | 0703 | SECURITY SYSTEMS UPGRADES
[24 empty] | 2007-12-03 | Dobson-E Rate | 802031.765 | 1491126.645 | 7358.33 |  |  |  | 2300516.74
[15 empty] | -12013 | [8 empty] | 2007-12-07 | Life Safety (0701.4) | 809390.095 | 1491126.645 |  |  |  | 12013 | 2288503.74 |  |  | 0701 | FIRE ALARM UPGRADES
[21 empty] | -211671 |  |  | 2007-12-07 | Russell Standard | 809390.095 | 1479113.645 |  |  |  | 211671 | 2076832.74 |  |  | 0714 | PARKING LOT IMPROVEMENT PROJECT
[12 empty] | -83760.3 | [11 empty] | 2007-12-07 | Life Safety (0701.4) | 809390.095 | 1267442.645 |  |  |  | 83760.3 | 1993072.44 |  |  | 0703 | SECURITY SYSTEMS UPGRADES
[19 empty] | -6010.68 |  |  |  |  | 2007-12-07 | Hewlett Packard Company | 809390.095 | 1183682.345 |  |  | 6010.68 |  | 1987061.76 |  |  |  | TECH-HP
[24 empty] | 2007-12-12 | Al Cox & Family-PES Auction | 803379.415 | 1183682.345 |  | 22645.65 |  |  | 2009707.41
[24 empty] | 2007-12-12 | Verizon-Erate | 803379.415 | 1206327.995 | 23865.18 |  |  |  | 2033572.59
[20 empty] | -15383.25 |  |  |  | 2007-12-13 | Innovative Construction & Mechanical LLC | 827244.595 | 1206327.995 |  |  |  | 15383.25 | 2018189.34 |  |  | 0705 | TECH ED LAB
[24 empty] | 2008-12-31 | December Interest | 827244.595 | 1190944.745 | 4243.555 | 4243.555 |  |  | 2026676.45
[19 empty] | -2615.05 |  |  |  |  | 2008-01-10 | Stone Consulting & Design | 831488.15 | 1195188.3 |  |  |  | 2615.05 | 2024061.4 |  |  |  | EMHS FLASHING SAFETY LIGHTS
[24 empty] | 2008-01-16 | One Communications-Erate | 831488.15 | 1192573.25 | 5908.18 |  |  |  | 2029969.58
[26 empty] | 837396.33 | 1192573.25
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 9306.7 | 0 | 98606.72 | 67353.14 | 0 | 0 | 35765.53 | 0 | 6837 | 23329 |  |  |  |  | 837396.33 | 1192573.25 |  |  |  |  | 2029969.58 | 0 | 2029969.58
[22 empty] | 245798.09 | 0 |  | ENCUMBERED | 0 | -245798.09 |  |  | ENCUMBERED |  | -245798.09 | 0
[25 empty] | AVAILABLE | 837396.33 | 946775.16 |  |  | AVAILABLE |  | 1784171.49 | 0
[24 empty] | PENDING BOARD BID APPROVAL |  | 0 | 0 |  |  | PENDING BOARD BID APPROVAL |  | 0 | 0
[24 empty] | PENDING BALANCE |  | 837396.33 | 946775.16 |  |  | PENDING BALANCE |  | 1784171.49 | 0
cross foot
[27 empty] | 2004-2005 | 601292.44 | 725180.76 | 22635.49 | 261985.88
[27 empty] | 2005-2006 | 180854.65 | 1279432.11 | 42696.5 | 428285.09 |  |  |  | afr | 470981.59
[27 empty] | YTD 2006-2007 | 292086.885 | 1283007.955 | 508762.1 | 664323.04 |  |  |  |  | 470534
[27 empty] | YTD 2007-2008 | 372595.345 | 48861.255 | 26583.16 | 937341.96 |  |  |  |  | 447.59
|  |  |  | 2004 OTHER TAB | [22 empty] | 2006-2007 DEPOSITS | 1575094.84 |  | 1173085.14 |  | 2006-2007 DISBURSEMENTS |  |  |  | diff
[27 empty] | 20O7-2008 DEPOSITS | 421456.6 |  | 963925.12 |  | 2007-2008 DISBURSEMENTS
Note on B6: turnquistp: paid by other means
Note on D6: turnquistp: wo 0301.04 4,800 -3000 adjust
Note on E6: JPT: ARCHITECTS 42,045
Note on L6: turnquistp: paid out of environmental acct in gen fund
Note on O5: turnquistp: EMHS 25,000 WAHS 250,000
Note on R6: turnquistp: paid out of environmental acct in gen fund
Note on S5: turnquistp: 34250 B & G 15,000 TECH
Note on S6: turnquistp: 10,000 TECH 34250 B & G
Note on AD120: turnquistp: estimate
Note on AM120: turnquistp: estimate

## (2) B & G ENCUMBRANCES
| 0502 | 0602 | 0601 | 0401 | 0602, 0508 | 0507, 507R | 0508 | 0508 | 0604 | 0604 | 0609 | 0703 | 0702 | 0704 | 0701 | 0709 | MASTER FACILITIES PLAN | FDK | OTHER | 0705 | 0714
COST | 87621 | 99010 | 79900 | 698000 | 20316 | 12451.73 | 2430 | 122629 | 13174.5 | 130000 | 5000 | 66200 | 0 | 275000 | 252000 | 79000 | 4385.64 | 34250 | 5940 | 200000 | 235000
NET ADJUSTMENT | -78858.9 | 4407.71 | 1800 | 33695 | 0 | 6124.25 | 0 | -3505.2 | 0 | 2580 | -5000 | 29803.2 | 0 | 0 | 0 | 0 | 8160.56 | 16925.53 | 12272.68 | 24129.47 | 0
| 2005-11-10 | 2006-08-22 | 2006-08-20 | 2004-10-01 | 2006-01-01 | 2006-01-19 | 2006-10-10 | 2006-07-31 | 2006-07-13 | 0 | 2006-10-18 | 2006-10-30 | 2006-08-30 | 2006-11-20 | 2006-11-20 | 2006-11-20 | 2007-04-19 | 0 |  | 2007-01-29 | 0
| AVE EMERG GENERATOR SERVER ROOM KEYSTONE ELECT | EMHS FIRE ALARM NORTHWEST SERVICE CO | BWMS EXTERIOR MASONRY ALLSTATE RESTORATION | WAHS ROOF JMST ROOFING | EMHS SEWAGE TR PLAN, 0602 ALARM SYSTEM 9,318.00 HF LENS. | BWMS, WAHS, EMHS WINDOW REPLACEMENT WTW ARCHITECTS | EMHS SEWAGE TREATMENT PLANT KEYSTONE ELECT | EMHS SEWAGE TREATMENT PLANT WM T SPAEDER CO INC, | SSELC PARK LOT, URBAN ENGINRS OF ERIE , & HRLC | SSELC PARKING LOT, KINGVVIEW ENTERPRISES | SGES VENTILATION SYSTEM, RADON OF ERIE | BWMS, EMHS, SAMHS, WCCC, WAHS, RES, SECURITY SYSTEM UPGRADE HF LENZ | WCCC WELD LAB ADDITION | WAHS & EMHS EXTERNAL ELECT UPGRADE | WCCC & SAMHS FIRE ALARM UPGRADE | SAMHS BLEACHERS | MASTER FACILITIES PLAN Studio Z Architects |  |  | WAHS, YEMS, YAHS, & EMHS TECH ED LAB PROJECT | Parking Lot Improvement Project
NET COST | 8762.1 | 103417.71 | 81700 | 731695 | 20316 | 18575.98 | 2430 | 119123.8 | 13174.5 | 132580 | 0 | 96003.2 | 0 | 275000 | 252000 | 79000 | 12546.2 | 51175.53 | 18212.68 | 224129.47 | 235000
PAYMENTS
2004-07-01 | 0 | 0 | 0 | 0 | 2008.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-07-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-07-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-08-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-09-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-09-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-09-24 | 0 | 0 | 0 | -261000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-12-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-01-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-02-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-02-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-02-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-03-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-03-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-06-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-06-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-07-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-08-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-08-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-08-29 | 0 | 0 | 0 | -108315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-09-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-09-07 | 0 | 0 | 0 | -259335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-09-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-09-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-10-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-10-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-11-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-10-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-12-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-01-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-04-10 | 0 | 0 | 0 | 0 | -12527.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-05-03 | 0 | 0 | 0 | 0 | -5733.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-06-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-07-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-07-13 | 0 | 0 | 0 | -25650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-07-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4074.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-08-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-08-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-08-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26759.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-08-08 | 0 | -42944.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-08-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-09-06 | 0 | 0 | 0 | 0 | -2497.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-09-11 | 0 | -47586.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-09-19 | 0 | 0 | -61251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-09-26 | 0 | 0 | -15649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-09-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -117000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-10-03 | 0 | 0 | 0 | -35350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-10-10 | 0 | 0 | 0 | 0 | -1565.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-10-10 | 0 | 0 | 0 | 0 | 0 | -12451.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-10-18 | 0 | 0 | 0 | 0 | 0 | 0 | -2187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-11-29 | 0 | 0 | 0 | 0 | 0 | 0 | -243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-11-29 | 0 | 0 | 0 | 0 | 0 | -6124.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-12-07 | 0 | -12886.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-12-18 | -8762.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -87513.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-01-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-01-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3646.33 | 0 | 0 | 0 | 0 | 0 | 0
2007-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11624 | 0 | 0 | 0 | 0 | 0 | 0
2007-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-03-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-03-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-03-22 | 0 | 0 | -4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4907.2 | 0 | 0 | 0 | 0 | 0 | 0
2007-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1422.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4385.64 | 0 | 0 | 0 | 0
2007-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -181.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-06-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-06-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4265.11 | 0 | 0 | 0 | 0
2007-06-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17274.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-06-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -79000 | 0 | 0 | 0 | 0 | 0
2007-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-07-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -230 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-07-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4315.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-07-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2066.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-07-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-07-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1845.15 | 0 | 0 | 0 | 0
2007-07-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-07-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-08-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-08-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1845.15 | 0 | 0 | 0 | 0
2007-08-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2572.33 | 0 | 0 | 0 | 0 | 0 | 0
2007-08-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -97649.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-08-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -611 | 0
2007-08-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74128 | 0 | 0 | 0 | 0 | 0 | 0
2007-08-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10040 | 0 | 0 | 0
2007-08-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3280 | 0 | 0 | 0
2007-08-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2090 | 0 | 0 | 0
2007-08-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-08-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21215.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-09-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -564.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-09-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13455 | 0
2007-09-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -85.5 | 0
2007-09-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -205.15 | 0 | 0 | 0 | 0
2007-09-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75756 | 0 | 0 | 0 | 0 | 0 | 0
2007-09-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -85.5 | 0
2007-09-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76617.9 | 0
2007-09-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20119.5 | 0
2007-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-10-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12968.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-10-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-10-09 | 0 | 0 | 0 | -42045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-10-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5500 | 0 | 0
2007-10-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -171 | 0
2007-10-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -440 | 0 | 0
2007-10-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -85 | 0
2007-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-10-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19611 | 0
2007-10-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12161 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-10-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21483 | 0
2007-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-11-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3435.07 | 0
2007-11-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -46149.75 | 0
2007-11-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3646.95 | 0 | 0
2007-11-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2180.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2008-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-12-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-12-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-12-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12013 | 0 | 0 | 0 | 0 | 0 | 0
2007-12-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -211671
2007-12-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -83760.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-12-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6010.68 | 0 | 0
2007-12-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-12-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007-12-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15383.25 | 0
2008-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2008-01-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2615.05 | 0 | 0
2008-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BALANCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 9306.7 | 0 | 98606.72 | 67353.14 | 0 | 0 | 35765.53 | 0 | 6837 | 23329
cross foot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 245798.09
TECHNOLOGY-->
CAPITAL RESERVE ENCUMBRANCE REPORT | [21 empty] | APPROVED
Note on B5: turnquistp: paid by bond

## (3) OUTSTANDING
B&G Report on Outstanding Monies for Projects *
Project No. | Project Name | Architect / Engineer(s) / Contractor | BUDGETED BALANCE | Cost Center
508 | EMHS Sewage Treatment Plant | Keystone Electric | 0 | CR
508 | EMHS Sewage Treatment Plant | Wm. T. Spaeder | 0 | CR
601 | BWMS Masonary Re-pointing | HRLC | 0 | CR
602 | EMHS Fire Alarm System | Northwest Service Company | 0 | CR
604 | SSELC Parking Lot Improvements | HRLC | 4600 | CR
0507r | Window Replacement (re-design) | WTW Architects | 0 | CR
609 | Sugar Grove Mitigation System |  | 0 | CR
| Approved Contracts Outstanding |  | 0 | 0
ESTIMATES PENDING BOARD APPROVAL FOR CONTRACTS |  |  | ESTIMATE
701 | WCCC & SAMHS Fire Alarm Upgrades | HF LENZ | 67353.14 | CR | Engineering Fees Billed
702 | WCCC Welding Lab Addition | HRLC / HF LENZ / HF GRAYGO | 0 | CR | CANCELED
703 | Security System Upgrades at Six Schools | HF LENZ | 9306.7 | CR
704 | EMHS & WAHS Exterior Electrical Upgrade | HF LENZ | 98606.72 | CR
705 | Technology Education Labs | HRLC | 200000 | CR
709 | SAMHS Bleachers |  | 0 | CR
|  | Total Estimate of Architect / Engineer Work Orders Approved to date: | 200000 | -45798.09
* Estimated amounts as of 1/20/07
Work Orders to Architect / Engineer approved:
Project No. |  | PP&F Committee | Board
701 | WCCC & SAMHS Fire Alarm Upgrades | 2006-11-20 | 2006-12-04
702 | WCCC Welding Lab Addition | 2006-08-30 | 2006-09-11
703 | Security System Upgrades at Six Schools | 2006-10-30 | 2006-11-13
704 | WAHS Exterior Electrical Upgrade | 2006-11-20 | 2006-12-04
| EMHS Exterior Electrical Upgrade | 2007-01-29
705 | Technology Education Labs | 2007-01-29
709 | SAMHS Bleachers | 2006-11-20 | 2006-12-04

## Capital Res. Bank Acct. 2005-06
Capital Reserve Cash Account Activity
|  | Balances |  | Deposits (+) |  | Checks (-) |  | Running
Date | Description | Tech | B&G | Tech | B&G | Tech | B&G | Balance
2004-07-01 |  | -8755.74 | 148027.14 |  |  |  |  | 139271.4
2004-07-19 | Deposit-Specs | -8755.74 | 148027.14 |  | 400 |  |  | 139671.4
2004-07-26 | Auction-Lander | -8755.74 | 148427.14 |  | 4952.5 |  |  | 144623.9
2004-08-13 | Deposit-Specs | -8755.74 | 153379.64 |  | 50 |  |  | 144673.9
2004-07-31 | Interest-July | -8755.74 | 153429.64 | 24.05 | 24.06 |  |  | 144722.01
2004-08-31 | Interest-August | -8731.69 | 153453.7 | 26.5 | 26.5 |  |  | 144775.01
2004-09-08 | Reimbursement | -8705.19 | 153480.2 |  |  | 665.93 | 135995 | 8114.08
2004-09-24 | Deposit-Grant | -9371.12 | 17485.2 | 475487 |  |  |  | 483601.08
2004-09-24 | Reimbursement | 466115.88 | 17485.2 |  |  |  | 76875 | 406726.08
2004-09-30 | Interest-Sept | 466115.88 | -59389.8 | 15.59 | 15.59 |  |  | 406757.26
2004-10-26 | Reimbursement | 466131.47 | -59374.21 |  |  |  | 545.6 | 406211.66
2004-10-26 | Transfer | 466131.47 | -59919.81 |  | 250000 |  |  | 656211.66
2004-10-31 | Interest-Oct | 466131.47 | 190080.19 | 71.8 | 71.8 |  |  | 656355.26
2004-11-30 | Interest-Nov | 466203.27 | 190151.99 | 120.22 | 120.22 |  |  | 656595.7
2004-12-21 | Reimbursement | 466323.49 | 190272.21 |  |  |  | 430.88 | 656164.82
2004-12-31 | Interest-Dec | 466323.49 | 189841.33 | 116.48 | 116.48 |  |  | 656397.78
2005-01-18 | Sprint-E Rate | 466439.97 | 189957.81 | 7257.6 |  |  |  | 663655.38
2005-01-20 | Verison-E Rate | 473697.57 | 189957.81 | 111534.41 |  |  |  | 775189.79
2005-02-01 | Deposit-Specs | 585231.98 | 189957.81 |  | 250 |  |  | 775439.79
2005-02-08 | Interest-Jan | 585231.98 | 190207.81 | 130.83 | 130.83 |  |  | 775701.45
2005-02-16 | Reimbursement | 585362.81 | 190338.64 |  |  |  | 48130 | 727571.45
2005-02-23 | Tower Eng-Refund | 585362.81 | 142208.64 | 101.52 |  |  |  | 727672.97
2005-03-09 | Interest-Feb | 585464.33 | 142208.64 | 129.74 | 129.74 |  |  | 727932.45
2005-03-23 | Reimbursement | 585594.07 | 142338.38 |  |  | 2250 |  | 725682.45
2005-04-07 | Dobson-E Rate | 583344.07 | 142338.38 | 5273.57 |  |  |  | 730956.02
2005-04-11 | Gateway | 588617.64 | 142338.38 |  |  | 14087 |  | 716869.02
2005-04-11 | Interest-March | 574530.64 | 142338.38 | 138.67 | 138.67 |  |  | 717146.36
2005-04-14 | Reimbursement | 574669.31 | 142477.05 |  |  | 4852.68 |  | 712293.68
2005-04-28 | Reimbursement | 569816.63 | 142477.05 |  |  | 555.6 |  | 711738.08
2005-05-04 | AT & T - E Rate | 569261.03 | 142477.05 | 351.86 |  |  |  | 712089.94
2005-05-13 | Interest-April | 569612.89 | 142477.05 | 135.56 | 135.56 |  |  | 712361.06
2005-05-25 | Reimbursement | 569748.45 | 142612.61 |  |  | 49.28 |  | 712311.78
2005-06-27 | Interest-May | 569699.17 | 142612.61 | 149.56 | 149.56 |  |  | 712610.9
2005-06-27 | Reimbursement | 569848.73 | 142762.17 |  |  | 175 |  | 712435.9
|  |  |  | 601064.96 | 256711.51 | 22635.49 | 261976.48

## Capital Reserve Trans. 2005-06
Capital Reserve Transaction Activity
|  |  | Tech | B&G
Date | Check # | Description | Amount | Amount | Misc Info
2004-07-22 | 216 | VOID
2004-09-08 | 217 | GovConnection Inc | 65.93
2004-09-08 | 217 | XiTech | 56
2004-09-08 | 217 | Mouse Pads on Line | 544
2004-09-08 | 217 | Jamestown Roofing Inc |  | 135995 | WHS Roof
2004-09-24 | 218 | Jamestown Roofing Inc |  | 76875 | WHS Roof
2004-10-26 | 219 | HF Lenz Co |  | 545.6 | Sprinklers/WHS
2004-12-21 | 220 | HF Lenz Co |  | 430.88
2005-02-16 | 221 | Jamestown Roofing Inc |  | 48130 | WHS Roof
2005-03-23 | 222 | PSBA | 2250
2005-04-11 | 223 | Gateway | 14087
2005-04-14 | 224 | Gov Connection Inc | 4852.68
2005-04-28 | 225 | Charges | 555.6
2005-05-25 | 226 | Gov Connection Inc | 49.28
2005-06-27 | 227 | Emerald Data | 175
|  | Transactions Paid To Date | 22635.49 | 261976.48
|  |  | Tech | B&G
|  | Beginning Balance | -8755.74 | 148027.14
|  | Less: Disbursements | 22635.49 | 261976.48
|  | Add: Deposits | 601064.96 | 256711.51
|  | Current Balance | 569673.73 | 142762.17 | 712435.9

## Capital Reserve Trans. 04.05
Capital Reserve Transaction Activity
|  |  | Tech | B&G
Date | Check # | Description | Amount | Amount | Misc Info
2004-07-22 | 216 | VOID
2004-09-08 | 217 | GovConnection Inc | 65.93
2004-09-08 | 217 | XiTech | 56
2004-09-08 | 217 | Mouse Pads on Line | 544
2004-09-08 | 217 | Jamestown Roofing Inc |  | 135995 | WHS Roof
2004-09-24 | 218 | Jamestown Roofing Inc |  | 76875 | WHS Roof
2004-10-26 | 219 | HF Lenz Co |  | 545.6 | Sprinklers/WHS
2004-12-21 | 220 | HF Lenz Co |  | 430.88
2005-02-16 | 221 | Jamestown Roofing Inc |  | 48130 | WHS Roof
2005-03-23 | 222 | PSBA | 2250
2005-04-11 | 223 | Gateway | 14087
2005-04-14 | 224 | Gov Connection Inc | 4852.68
2005-04-28 | 225 | Charges | 555.6
2005-05-25 | 226 | Gov Connection Inc | 49.28
2005-06-27 | 227 | Emerald Data | 175
|  | Transactions Paid To Date | 22635.49 | 261976.48
|  |  | Tech | B&G
|  | Beginning Balance | -8755.74 | 148027.14
|  | Less: Disbursements | 22635.49 | 261976.48
|  | Add: Deposits | 601064.96 | 256711.51
|  | Current Balance | 569673.73 | 142762.17 | 712435.9

## Needs
| Tech |  | B&G
July - Sept 2005 | 100000 | Misc | 177000 | WAHS Roofing
|  |  | 15000 | Sheffield Paving
|  |  | 52000 | WAHS Paving
|  |  | 30000 | Misc
| 100000 |  | 274000
RECONCILIAITON
| 2006-08-28 | 1724256.57
-26759.7
|  | -4851 |  | 4064.56
|  | -42944.97 |  | 12527.2
-25650
1624050.9
|  | -405918.68 |  | 16591.76 | due to gen fund 8/28/06
100205.67
-305713.01