## Tentative Timeline
WCSD
2015-2016 Budget Adoption
Detailed Timeline
DRAFT - 10.27.14
Actual # Days
Prior to | Date to be
Primary Election | Completed | Description of Activity to be completed
| 2014-11-17 | Superintendent conducts an internal review and comparison of the budget, reviewing prior year's actuals against the
| COMMITTEE MTG | approved budget, and presents to the Board of School Directors the comparison of the rough-cut budget outlining
estimated revenues, expenditures, and associated assumptions used in developing the estimates. Board Policy 4020.2
| 2014-12-15 | Board in partnership with the Superintendent refines goals based on rough-cut budget. Board Policy 4020.2
TENTATIVE DATE
| 2015-01-12 | Board directs Board Secretary to Advertise Public Notice of Intent to approve the 2015-2016 Preliminary Budget at the
| BOARD MEETING | February 9, 2015 Board meeting no later than |  | 2015-01-30 | as must give 10 days notice unless resolution adopted not to raise the rate
of any tax by more than its index. Deadline to give Public Notice is 2/8/15 or 10 days prior to preliminary budget adoption deadline.
| 2015-01-26 | Superintendent presents to the Board either a "Proposed Preliminary Budget" or a recommended resolution indicating taxes will
| COMMITTEE MTG | not be raised above the "Index." The Board of School Directors acts on Superintendent's recommendation as mandated by PDE
| SPECIAL BOARD MTG? | under Act 1.
Intent here is to get any additional input if any changes are needed from Proposed Preliminary Budget before Preliminary Budget is
approved on February 9, 2015.
Special Board Meeting is only needed if Board chooses to adopt a resolution pursuant to Section 311(d)(1) indicating that it will not
raise the rate of any tax by more than its index or if Board does not direct to advertise public notice at 1/12/15 meeting of intent to approve Proposed Budget on 2/9/15
Special Board Meeting: Board directs Board Secretary to Advertise Public Notice of Intent to approve the 2015-2016 Preliminary Budget at the
|  | February 9, 2015 Board meeting no later than |  | 2015-01-30 | as must give 10 days notice unless resolution adopted not to raise the rate
of any tax by more than its index. Deadline to give Public Notice is 2/8/15 or 10 days prior to preliminary budget adoption deadline.
112 | 2015-01-27 | School District to make 2015-2016 Proposed Preliminary Budget available for public inspection unless resolution adopted
pursuant to Section 311(d)(1) indicating that it will not raise the rate of any tax by more than its index.
|  | 112 | days before the Primary Election. Section311©; 311(d)(1) - DEADLINE IS 1/29/15 OR 110 DAYS PRIOR TO PRIMARY ELECTION
| 2015-01-31 | Deadline to submit a copy of resolution adopted pursuant to 311(d)(1) and proposed tax rate increases to
|  | Department of Education if Board decided not to raise taxes above index. Section 311(d)(2). |  |  |  | 5 | DAYS AFTER RESOLUTION ADOPTION.
99 | 2015-02-09 | Board votes to approve Preliminary Budget as presented. Directs the administration to submit the preliminary
| BOARD MEETING | Budget and proposed tax rate increases to PDE on or before February 23, 2015; Directs the Board Secretary
to publish the required notice of intent to file for referendum exceptions on or before February 26, 2015;
and authorizes the administration to apply for PDE for referendum exceptions prior to the March 5, 2015,
deadline. Deadline to adopt the Preliminary Budget is 2/18/15 AND must be 90 days before Primary Election.
| 2015-02-23 | Business Administrator conducts Budget Workshops with the Board Finance committee to review projected revenues, line item expenditures,
| COMMITTEE MTG | and staffing and requests for new programs, services or personnel. Board Policy 4020.2
| 2015-02-26 | School District deadline to publish notice in newspaper of intent to request approval from Department of Education
for a referendum exception. Section 333(j)(2)
75 | 2015-03-05 | Deadline for School District to seek approval from Department of Education for referendum exceptions requiring their approval. Section 333(c)(3)
Deadline is 75 days prior to primary election. Section 333(j)
| 2015-03-09 | Provide Board with update on Budget progress.
BOARD MEETING
| 2015-03-23 | Business Administrator conducts Budget Workshops with the Board Finance committee to review projected revenues, line item expenditures,
| COMMITTEE MTG | and staffing and requests for new programs, services or personnel. Board Policy 4020.2
Provide Analysis to board on Act 1 versus Labor, PSERS, FICA and Medical expenditures. Provide to board updated Tentative Timeline for Budget
adoption.
| 2015-04-13 | Superintendent report on budget status. Provide Administration recommended cuts/adds, if available.
BOARD MEETING
| 2015-04-27 | Superintendent prepares and presents a Proposed Budget to the Finance Committee. Board Policy 4020.2
| COMMITTEE MTG | Recommendations provided to board from Administration on potential cuts/adds. Board provides guidance to Administration
on cuts/adds.
Business Administrator conducts Budget Workshops with the Board Finance committee to review projected revenues, line item expenditures,
and staffing and requests for new programs, services or personnel. Board Policy 4020.2
| 2015-05-11 | Board Finance Committee recommends Proposed School Budget to the Board of School Directors. Board Policy 4020.2
| BOARD MEETING | Approve the 2015-2016 Proposed Final Budget and mail Certification of use of PDE 2028 to the Dept of Ed. |  |  |  |  | Section 687 (a)(1)
* Must be done no later than May 31, 2015
Days Before Final
26 | 2015-05-13 | Make 2015-2016 proposed final budget available for public inspection on PDE - 2028. Section 312 ( c )
* Due 20 days prior to final budget adoption deadline.
| 2015-05-19 | PRIMARY ELECTION
| 2015-05-25 | Budget discussion at committee.
COMMITTEE MTG
| SPECIAL BOARD MTG? | Potential special board meeting if Proposed Final Budget is not approved on 5/11/15.
11 | 2015-05-28 | School District advertises to offer public notice of its intent to adopt the 2015-2016 Final Budget. Section 312 ( c ); Section 687(a)(2)(i)
* Due 10 days prior to final budget adoption date.
| 2015-06-08 | Adopt Final Budget. Section 312 (a)
| BOARD MEETING | Adopt resolution for homestead/farmstead exclusion. Section 505 (a)(4)
Tax Structure and resource allocation resolution.
Annual resolution for Act 1 (installment payments)
* Annual deadline is June 30th.
Board of School Directors adopts Final School Budget and certifies that the Final Budget complied with the requirements of Section 687
of the School Code. Board Policy 4020.2
| 2015-07-15 | School District deadline to submit 2015-2016 Final Budget to Department of Education on PDE form 2028. Section 687 (b)
Note: Discussion will occur with Finance Chair on timing of Budget Workshop meetings with Finance Committee.