## Timeline 2016
WCSD
2016-2017 Budget Adoption
Detailed Timeline
2.29.16
Actual # Days
Prior to | Date to be
Primary Election | Completed | Description of Activity to be completed
| 2015-11-09 | Superintendent conducts an internal review and comparison of the budget, reviewing prior year's actuals against the
| BOARD MEETING | approved budget, and presents to the Board of School Directors the comparison of the rough-cut budget outlining
estimated revenues, expenditures, and associated assumptions used in developing the estimates. Board Policy 4020.2
| 2015-11-16 | Budget Discussion as needed
COMMITTEE
| 2015-12-07 | Budget Discussion as needed
ORGANIZATION MEETING
BOARD MEETING
| 2015-12-21 | Board in partnership with the Superintendent refines goals based on rough-cut budget. Board Policy 4020.2
COMMITTEE
| SPECIAL BOARD MEETING | Board directs Board Secretary to Advertise Public Notice of Intent to approve the 2016-2017 Proposed Preliminary Budget at the
|  | January 25, 2016 Special Board meeting. Must be done 10 days in advance or no later than |  | 2016-01-15
| 2016-01-04 | OR adopt resolution that the district with not raise the rate of any tax by more than its index. Deadline to give Public Notice
| SPECIAL BOARD MEETING | is 1/17/16 but must be 10 days prior to Proposed Preliminary Budget adoption (Deadline to adopt is 1/27/16).
(IF NOT ON 12/14 OR 12/21)
110 | 2016-01-07 | School District to make 2016-2017 Proposed Preliminary Budget available for public inspection (on or before January 7) unless resolution adopted
pursuant to Section 311(d)(1) indicating that it will not raise the rate of any tax by more than its index.
|  | 110 | days before the Primary Election. Section311©; 311(d)(1) - DEADLINE IS 1/7/16 OR 110 DAYS PRIOR TO PRIMARY ELECTION
| 2016-01-11 | Budget discussion as necessary.
BOARD MEETING
| 2016-01-12 | If resolution adopted, School District deadline to submit a copy of resolution adopted pursuant to 311(d)(1) and proposed tax rate increases to Department of Education.
Section 311(d)(2).
| 2016-01-25 | Budget discussion as necessary.
| COMMITTEE MTG | * Map timeline
| SPECIAL BOARD MTG | * Discuss deliverables
| 2016-02-08 | Budget discussion as necessary.
BOARD MEETING
| 2016-02-29 | Business Administrator conducts Budget Workshops with the Board Finance committee to review projected revenues, line item expenditures,
| COMMITTEE MTG | and staffing and requests for new programs, services or personnel. Board Policy 4020.2
* Discuss 5 & 7 Year plans for Technology, Textbooks and Buildings & Grounds.
* Discuss Adds and Cuts - Preliminary listing - CUTS NOT PREPARED AT THIS TIME.
| 2016-03-14 | Provide Board with update on Budget progress.
BOARD MEETING
| 2016-03-28 | Business Administrator conducts Budget Workshops with the Board Finance committee to review projected revenues, line item expenditures,
| COMMITTEE MTG | and staffing and requests for new programs, services or personnel. Board Policy 4020.2
* Recommendations provided to board from Administration on potential adds/cuts.
* Board provides guidance to Administration on Adds/Cuts. Vote on Adds/Cuts (?)
* Budget for 2016-2017 and 5 Year projection.
| 2016-04-11 | Budget discussion if necessary.
BOARD MEETING
| 2016-04-25 | Superintendent prepares and presents a Proposed Budget to the Finance Committee. Board Policy 4020.2
| COMMITTEE MTG | Business Administrator conducts Budget Workshops with the Board Finance committee to review projected revenues, line item expenditures,
and staffing and requests for programs, services or personnel. Board Policy 4020.2
Discusion on Adds/Cuts, as necessary.
| 2016-04-26 | GENERAL PRIMARY ELECTION
| 2016-05-09 | Budget discussion if necessary. Approve Proposed Final Budget if completed.
BOARD MEETING
Board Finance Committee recommends Proposed School Budget to the Board of School Directors. Board Policy 4020.2
|  | Approve the 2016-2017 Proposed Final Budget and mail Certification of use of PDE 2028 to the Dept of Ed. |  |  | Section 687 (a)(1)
School Board authorizes Administration to advertise of its intent to approve the Final Budget at the 6/20/16 special board meeting
* Proposed Final Budget must be submitted no later than May 31, 2016
| 5/16,17 or 18 | If Board does not adopt Proposed Final Budget at 5/9/16 board meeting.
SPECIAL BOARD MTG
Days Before Final
24 | 2016-05-20 | Make 2016-2017 Proposed Final Budget available for public inspection on PDE - 2028. Section 312 ( c )
* Due 20 days prior to final budget adoption deadline.
19 | 2016-05-25 | School District advertises to offer public notice of its intent to adopt the 2016-2017 Final Budget. Section 312 ( c ); Section 687(a)(2)(i)
* Due 10 days prior to final budget adoption date.
| 2016-05-31 | Budget discussion at committee.
COMMITTEE MTG
| 2016-06-13 | Adopt Final Budget. Section 312 (a)
| BOARD MEETING | Adopt resolution for homestead/farmstead exclusion. Section 505 (a)(4)
Tax Structure and resource allocation resolution.
Annual resolution for Act 1 (installment payments)
* Annual deadline is June 30th.
Board of School Directors adopts Final School Budget and certifies that the Final Budget complied with the requirements of Section 687
of the School Code. Board Policy 4020.2
| 2016-06-27 | Adopt Final Budget. Section 312 (a) IF NOT DONE ON 6/13/16
| COMMITTEE MTG | Adopt resolution for homestead/farmstead exclusion. Section 505 (a)(4)
| SPECIAL BOARD MTG | Tax Structure and resource allocation resolution.
Annual resolution for Act 1 (installment payments)
* Annual deadline is June 30th.
Board of School Directors adopts Final School Budget and certifies that the Final Budget complied with the requirements of Section 687
of the School Code. Board Policy 4020.2
| 2016-07-15 | School District deadline to submit 2016-2017 Final Budget to Department of Education on PDE form 2028. Section 687 (b)

## Tentative Timeline
WCSD
2016-2017 Budget Adoption
Detailed Timeline
DRAFT - 11.9.15
Actual # Days
Prior to | Date to be
Primary Election | Completed | Description of Activity to be completed
| 2015-11-09 | Superintendent conducts an internal review and comparison of the budget, reviewing prior year's actuals against the
| BOARD MEETING | approved budget, and presents to the Board of School Directors the comparison of the rough-cut budget outlining
estimated revenues, expenditures, and associated assumptions used in developing the estimates. Board Policy 4020.2
| 2015-11-16 | Budget Discussion as needed
COMMITTEE
| 2015-12-07 | Budget Discussion as needed
ORGANIZATION MEETING
BOARD MEETING
| 2015-12-21 | Board in partnership with the Superintendent refines goals based on rough-cut budget. Board Policy 4020.2
COMMITTEE
| SPECIAL BOARD MEETING | Board directs Board Secretary to Advertise Public Notice of Intent to approve the 2016-2017 Proposed Preliminary Budget at the
|  | January 25, 2016 Special Board meeting. Must be done 10 days in advance or no later than |  | 2016-01-15
| 2016-01-04 | OR adopt resolution that the district with not raise the rate of any tax by more than its index. Deadline to give Public Notice
| SPECIAL BOARD MEETING | is 1/17/16 but must be 10 days prior to Proposed Preliminary Budget adoption (Deadline to adopt is 1/27/16).
(IF NOT ON 12/14 OR 12/21)
110 | 2016-01-07 | School District to make 2016-2017 Proposed Preliminary Budget available for public inspection (on or before January 7) unless resolution adopted
pursuant to Section 311(d)(1) indicating that it will not raise the rate of any tax by more than its index.
|  | 110 | days before the Primary Election. Section311©; 311(d)(1) - DEADLINE IS 1/7/16 OR 110 DAYS PRIOR TO PRIMARY ELECTION
| 2016-01-11 | Budget discussion as necessary.
BOARD MEETING
| 2016-01-12 | If resolution adopted, School District deadline to submit a copy of resolution adopted pursuant to 311(d)(1) and proposed tax rate increases to Department of Education.
Section 311(d)(2).
92 | 2016-01-25 | Board votes to approve Preliminary Budget as presented. Directs the administration to submit the preliminary
| COMMITTEE MTG | Budget and proposed tax rate increases to PDE on or before February 1, 2016; Directs the Board Secretary
| SPECIAL BOARD MTG | to publish the required notice of intent to file for referendum exceptions on or before February 4, 2016( Section 333(j)(2): 1 week before referendum exceptions must be filed);
and authorizes the administration to apply for PDE for referendum exceptions prior to the February 11, 2016
deadline (Section 333 ( j ) 75 days prior to primary election). Deadline to adopt the Preliminary Budget is 1/27/16 AND must be 90 days before Primary Election.
| 2016-02-04 | Deadline to publish intent to file for referendum exceptions. Section 333(j)(2)
| 2016-02-08 | Budget discussion as necessary.
BOARD MEETING
| 2016-02-11 | Deadline to apply for referendum exceptions. Section 333 ( j )
| 2016-02-29 | Business Administrator conducts Budget Workshops with the Board Finance committee to review projected revenues, line item expenditures,
| COMMITTEE MTG | and staffing and requests for new programs, services or personnel. Board Policy 4020.2
| 2016-03-14 | Provide Board with update on Budget progress.
BOARD MEETING
| 2016-03-28 | Business Administrator conducts Budget Workshops with the Board Finance committee to review projected revenues, line item expenditures,
| COMMITTEE MTG | and staffing and requests for new programs, services or personnel. Board Policy 4020.2
| 2016-04-11 | Budget discussion if necessary.
BOARD MEETING
| 2016-04-25 | Superintendent prepares and presents a Proposed Budget to the Finance Committee. Board Policy 4020.2
| COMMITTEE MTG | Recommendations provided to board from Administration on potential cuts/adds. Board provides guidance to Administration
on cuts/adds.
Business Administrator conducts Budget Workshops with the Board Finance committee to review projected revenues, line item expenditures,
and staffing and requests for programs, services or personnel. Board Policy 4020.2
| 2016-04-26 | GENERAL PRIMARY ELECTION
| 2016-05-09 | Budget discussion if necessary.
BOARD MEETING
| 2016-05-31 | Budget discussion at committee.
COMMITTEE MTG
| SPECIAL BOARD MTG | Board Finance Committee recommends Proposed School Budget to the Board of School Directors. Board Policy 4020.2
|  | Approve the 2016-2017 Proposed Final Budget and mail Certification of use of PDE 2028 to the Dept of Ed. |  |  | Section 687 (a)(1)
School Board authorizes Administration to advertise of its intent to approve the Final Budget at the 6/20/16 special board meeting
* Proposed Final Budget must be submitted no later than May 31, 2016
Days Before Final
33 | 2016-05-25 | Make 2016-2017 Proposed Final Budget available for public inspection on PDE - 2028. Section 312 ( c )
* Due 20 days prior to final budget adoption deadline.
21 | 2016-06-06 | School District advertises to offer public notice of its intent to adopt the 2016-2017 Final Budget. Section 312 ( c ); Section 687(a)(2)(i)
* Due 10 days prior to final budget adoption date.
| 2016-06-13 | Budget Discussion if necessary.
BOARD MEETING
| 2016-06-27 | Adopt Final Budget. Section 312 (a) IF NOT DONE ON 6/13/16
| COMMITTEE MTG | Adopt resolution for homestead/farmstead exclusion. Section 505 (a)(4)
| SPECIAL BOARD MTG | Tax Structure and resource allocation resolution.
Annual resolution for Act 1 (installment payments)
* Annual deadline is June 30th.
Board of School Directors adopts Final School Budget and certifies that the Final Budget complied with the requirements of Section 687
of the School Code. Board Policy 4020.2
| 2016-07-15 | School District deadline to submit 2016-2017 Final Budget to Department of Education on PDE form 2028. Section 687 (b)