## B&G 7 Year
Buildings & Grounds
7 Year Project Planning Worksheet
Draft 02.25.19
|  |  |  | Project Year | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  |  |  | 2018-2019 | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026
|  |  | Buildings and Grounds (as presented in 5 yr Budget) | 300000 | 500000 | 700000 | 900000 | 1100000 | 1300000 | 1500000 | 1700000
|  |  | Beginning Capital Reserve Balance | 1924024.76 | 104024.76 | -4404475.24 | -5825475.24 | -8331475.24 | -8221475.24 | -7821475.24 | -7651475.24
|  |  | Request for Additional Funding | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
|  |  | TOTAL MONEY AVAILABLE TO USE | 2424024.76 | 804024.76 | -3504475.24 | -4725475.24 | -7031475.24 | -6721475.24 | -6121475.24 | -5751475.24
BUILDING | SYSTEM | LIFE EXPECTANCY | PROJECT DETAIL | 2018-2019 | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026
BWMS | EXTERIOR | 20 | BWMS Vent Repair | 2019-2020: 66000; 2020-2021: 66000; 2021-2022: 66000; 2022-2023: 65000
BWMS | EXTERIOR | 30 | BWMS Roof Replacement | 2018-2019: 1200000
BWMS | EXTERIOR | 40 | BWMS Shingles (Last Install 1994) | 2024-2025: 500000
BWMS | INTERIOR | 20 | BWMS Stairwell Flooring Replacement | 2020-2021: 20000; 2021-2022: 20000
CO | ELECTRICAL / TECH | 15 | RES/CO Fiber Replacement, MDF, Copper Wiring CAT5 Replacement | 2021-2022: 100000; 2022-2023: 100000
CO | EXTERIOR / ROOF | 20 | CO Roof Replacement | 2024-2025: 500000
EMHS/EES | EXTERIOR | 20 | EMHS/EES Storage Building | 2019-2020: 75000; 2020-2021: 100000
EMHS/EES | PLUMBING | 20 | EMHS/EES Domestic Water Treatment | 2020-2021: 20000
EMHS/EES | ROOFING / EXTERIOR | 20 / 30 | EMHS/EES Roof (Exp. 2021, except Aud./'68 wing) | 2019-2020: 1700000
SAMHS | ELECTRICAL | 20 | SAMHS Auditorium Lighting | 2018-2019: 30000
SAMHS | HVAC | 20 | SAMHS Vertical Uninvents (HVAC) |  |  | 400000 | 400000 | 400000 | 400000 | 160000 | 240000
SAMHS | INTERIOR | 20 | SAMHS Auditorium Seating | 2020-2021: 70000; 2021-2022: 90000
SAMHS | INTERIOR | 20 | SAMHS Gym Bleachers Upgrade | 2020-2021: 90000
SAMHS | PLUMBING | 20 | SAMHS Fire Suppression System | 2021-2022: 818000
SAMHS/SAES | EXTERIOR | 30 | SAMHS/SAES K-12 Roofing | 2019-2020: 2000000
SAMHS/SAES | FOOD SERVICE | 15 | SAMHS/SAES K-12 Kitchen Serving Line Upgrade | 2020-2021: 125000
WAHS | EXTERIOR | 20 | WAHS Guide Rail - Lawn Ave. | 2018-2019: 75000
WAHS | INTERIOR | 15 | WAHS Auditorium - Sound System | 2018-2019: 90000
WAHS | INTERIOR | 20 | WAHS Auditorium - Stage Curtains | 2018-2019: 50000
WAHS | ELECTRICAL | 20 | WAHS Parking Lot Campus - LED Lights Retrofit | 2019-2020: 50000
WARREN CAMPUS | ELECTRICAL | 10 | Warren Campus Parking Lot Light Upgrades (LED Retro-fit) | 2019-2020: 25000
YEMS | ELECTRICAL | 20 | YEMS CCTV Upgrade | 2019-2020: 25000; 2020-2021: 25000
YEMS | ELECTRICAL | 20 | YEMS Network Cabinet / Copper Wiring CAT5 Replacement | 2019-2020: 75000; 2020-2021: 75000; 2021-2022: 75000; 2022-2023: 75000
YEMS | ELECTRICAL | 20 | YEMS PA System Upgrade | 2020-2021: 30000
YEMS | EXTERIOR | 10 | YEMS Parking Lot Sealing / Repair | 2018-2019: 25000
YEMS | EXTERIOR | 20 | YEMS Roof - Phase I | 2018-2019: 400000
YEMS | EXTERIOR | 20 | YEMS Roof - Phase II | 2019-2020: 500000
YEMS | HVAC | 20 | YEMS Vertical Uninvents |  |  | 400000 | 400000 | 400000 | 400000 | 160000 | 240000
YEMS | PLUMBING | 20 | YEMS Boiler Replacement (2) | 2020-2021: 150000
YEMS | PLUMBING | 20 | YEMS Boilers (1) - Phase II Addition | 2020-2021: 75000
YEMS | PLUMBING | 20 | YEMS Fire Suppression System | 2021-2022: 812000
YEMS | PLUMBING | 20 | YEMS Hot Water Tank Replacement | 2019-2020: 50000
DISTRICT | DISTRICT | 20 | Siemens System Upgrade (Software) | 2019-2020: 67500
DISTRICT | DISTRICT | 20 | Siemens System Upgrade (Hardware) | 2019-2020: 50000; 2020-2021: 50000
DISTRICT | DISTRICT | 1 | Hazmat Chemical inventory & Disposal | 25000 | 25000 | 25000 | 250000 | 25000 | 25000 | 25000 | 25000
DISTRICT | DISTRICT | 1 | Parking Lot Painting & Sealing | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
DISTRICT | DISTRICT | 20 | Freezer and Refrigeration Monitoring | 2019-2020: 10000; 2020-2021: 10000
DISTRICT | DISTRICT | 20 | Safety Bollards | 2019-2020: 15000; 2020-2021: 15000
DISTRICT | DISTRICT | 20 | State Police Safety Recommendations | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
DISTRICT | DISTRICT |  | Custodial Equipment |  | 50000 | 150000 | 150000 |  | 150000 |  | 150000
DISTRICT | DISTRICT |  | Grounds Equipment | 2024-2025: 60000; 2025-2026: 60000
DISTRICT | DISTRICT |  | Vehicle/Fleet Replacements | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
DISTRICT | DISTRICT |  | Electrical Open-ended Contract Labor | 2018-2019: 100000; 2019-2020: 100000; 2020-2021: 100000; 2021-2022: 100000
DISTRICT | DISTRICT |  | Carpentry Open-ended Contract Labor | 2018-2019: 100000; 2019-2020: 100000; 2020-2021: 100000; 2021-2022: 100000
DISTRICT | DISTRICT |  | Moving Crew Open-ended Contract Labor | 2018-2019: 100000; 2019-2020: 100000; 2020-2021: 100000; 2021-2022: 100000
|  |  | TOTAL | 2320000 | 5208500 | 2321000 | 3606000 | 1190000 | 1100000 | 1530000 | 840000
[9 empty] | 7 YEAR TOTAL |  | 15795500
|  |  | SUMMARY | 2018-2019 | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026
|  |  | Total Budgeted (W/ADDS) | 500000 | 700000 | 900000 | 1100000 | 1300000 | 1500000 | 1700000 | 1900000
|  |  | Total Expended | 2320000 | 5208500 | 2321000 | 3606000 | 1190000 | 1100000 | 1530000 | 840000
|  |  | Capital Reserve Balance (Use)/Add | -1820000 | -4508500 | -1421000 | -2506000 | 110000 | 400000 | 170000 | 1060000
|  |  | SUMMARY CAPITAL RESERVE BALANCE | 2018-2019 | 2019-2020 | 2020-2021 | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026
|  |  | STARTING BALANCE | 1924024.76 | 104024.76 | -4404475.24 | -5825475.24 | -8331475.24 | -8221475.24 | -7821475.24 | -7651475.24
|  |  | (USE)/ADD OF CAPITAL RESERVE | -1820000 | -4508500 | -1421000 | -2506000 | 110000 | 400000 | 170000 | 1060000
|  |  | PROJECTED CAPITAL RESERVE BALANCE | 104024.76 | -4404475.24 | -5825475.24 | -8331475.24 | -8221475.24 | -7821475.24 | -7651475.24 | -6591475.24