## Project Timelines
| PPF Forward Motion to approve work order to Architects /Engineers | Board Meeting approve work order to Architects /Engineers | Execute Work Order between District and Architect /Engineer | Request for Prevailing Wage Determination -Depart of L&I | Begin steps to Design Project/Write Technical Specifications | PPF Forward Motion to Submit Form 3074 (a,b,c) | Uniform Construction Code - Building Permit | Write Legal Advertisement - Advertise for 3 consectutive weeks in newspaper | Board Meeting Approve submission of PDE Form 3074 (a,b,c) | Merge Front End with Design Specifications - Send to Printer | Pre-Bid Conference with Potential Bidders | Bid-Date Accept Proposals | PPF Forward Motion to approve awarding bids | Board Meeting Approve Bids | Letter Requesting Bond and Insurance Certificate | Write Construction Contracts | Mail Notice of Award Letter with two (2) Original Contracts | Return Bid Bonds to disappointed Bidders | School Board President executes Contracts | Return one (1) Fully executed Contract with Notice to Proceed Letter | Project Start Date | Estimated Project End Date
Task Start Date | 2006-01-31 | 2006-02-13 | 2006-02-13 | 2006-02-27 | 2006-03-06 | 2006-03-28 | 2006-03-28 | 2006-04-03 | 2006-04-10 | 2006-04-11 | 2006-04-17 | 2006-04-21 | 2006-04-28 | 2006-05-08 | 2006-05-09 | 2006-05-09 | 2006-05-15 | 2006-05-19 | 2006-05-29 | 2006-06-02 | 2006-06-12 | 2006-08-21
EMHS Fire Alarm System Upgrade Project #0602 | 100% 1/31/06 | 100% 2/13/06 | 100% 3/13/06 | 100% 4/6/06 | 100% complete | 100% 4/10/06 | Application complete | 100% 4/6/06 | 100% 4/10/06 | 100% 4/12/06 | 100% 4/18/06 | 100% 4/21/06 | 100% 4/25/06 | 100% 5/8/06 | 100% 5/9/06 | 100% 5/18/06 | 100% 5/19/06 | 100% 5/23/06 | 100% 6/07/06 | 100% 6/07/06 | 100% 6/12/06 |  | EMHS Fire Alarm System Upgrade Project #0602
Task Start Date | 2006-01-31 | 2006-02-13 | 2006-02-13 | 2006-02-27 | 2006-03-06 | 2006-03-28 | 2006-03-28 | 2006-04-03 | 2006-04-10 | 2006-04-11 | 2006-04-17 | 2006-04-21 | 2006-04-28 | 2006-05-08 | 2006-05-09 | 2006-05-09 | 2006-05-15 | 2006-05-19 | 2006-05-29 | 2006-06-02 | 2006-06-12 | 2006-08-21
EMHS Sewage Treatment Plant Improvements Project #0508 | 100% 1/31/06 | 100% 2/13/06 | 100% 2/15/06 | 100% 4/6/06 | 100% complete | 100% 4/10/06 | Application complete | 100% 4/6/06 | 100% 4/10/06 | 100% 4/12/06 | 100% 4/18/06 | 100% 4/21/06 | 100% 4/25/06 | 100% 5/8/06 | 100% 5/9/06 | 100% 5/18/06 | 100% 5/19/06 | 100% 5/23/06 | 100% 5/30/06 | 100% 5/30/06 | 100% 6/12/06 |  | EMHS Sewage Treatment Plant Improvements Project #0508
Task Start Date | 2006-01-31 | 2006-02-13 | 2006-02-13 | 2006-02-27 | 2006-03-06 | 2006-03-28 | 2006-03-28 | 2006-04-03 | 2006-04-10 | 2006-04-11 | 2006-04-17 | 2006-04-21 | 2006-04-28 | 2006-05-08 | 2006-05-09 | 2006-05-09 | 2006-05-15 | 2006-05-19 | 2006-05-29 | 2006-06-02 | 2006-06-12 | 2006-08-21
BWMS Exterior Masonry Repointing Project #0601 | 100% 1/31/06 | 100% 2/13/06 | 100% 3/30/06 | 100% 4/6/06 | 100% complete | 100% 4/10/06 | N/A | 100% 4/11/06 | 100% 4/10/06 | 100% 4/17/06 | 100% 4/24/06 | 100% 5/4/06 | ammended minutes 100% 5/4/06 | 100% 5/8/06 | 100% 5/9/06 | 100% 5/18/06 | 100% 5/19/06 | 100% 5/23/06 | 100% 6/01/06 | 100% 6/01/06 | 100% 6/12/06 |  | BWMS Exterior Masonry Repointing Project #0601
Task Start Date | 2005-10-24 | 2005-11-14 | 2005-11-14
Replacement Window BWMS/WAHS/EMHS Project #0507 | 100% 10/24/05 | 100% 11/14/05 | 100% 11/16/05 | RE-DESIGN IN PROGRESS | [18 empty] | Replacement Window BWMS/WAHS/EMHS Project #0507
Task Start Date | 2006-04-25 | 2006-05-08 | 2006-05-10 | 2006-04-06 | 2006-04-10 | 2006-04-10 |  | 2006-05-03 | 2006-05-08 | 2006-05-18 | 2006-05-17 | 2006-05-30 | 2006-06-01 | 2006-06-12 | 2006-06-13 | 2006-06-13 | 2006-06-23 | 2006-06-23 | 2006-06-26 | 2006-06-26 |  | 2006-08-21
SSELC Parking Lot Project #0604 | 100% 4/25/06 | 100% 5/8/06 | 100% 5/19/06 | 100% 4/6/06 | 100% complete 4/10/06 | 100% 4/25/06 | Application complete | 100% 5/3/06 | 100% 5/8/06 | 100% 5/18/06 | 100% 5/17/06 | 100% 5/31/06 | 100% 6/01/06 | 100% 6/12/06 | 100% 6/13/06 | 100% 6/13/06 | [6 empty] | SSELC Parking Lot Project #0604