## Project Timelines
| PPF Forward Motion to approve work order to Architects /Engineers | Board Meeting approve work order to Architects /Engineers | PPF Forward Motion to Submit Form 3074 (a,b,c) | Board Meeting Approve submission of PDE Form 3074 (a,b,c) | Forward 3074 (a,b,c) to PDE for Approval | Received Approved 3074 (a,b,c) from PDE | Send Work Order to Architect / Engineer for Signature | Execute Work Order between District and Architect /Engineer | Begin steps to Design Project/Write Technical Specifications | Request for Prevailing Wage Determination -Depart of L&I | Received Prevailing Wage Determination - Depart of L&I | Merge Front End with Design Specifications - Send to Printer | Write Legal Advertisement - Advertise for 3 consectutive weeks in newspaper | Pre-Bid Conference with Potential Bidders | Bid-Date Accept Proposals | PPF Forward Motion to approve awarding bids | Board meeting to approve awarding bids | Apply for Uniform Construction Code - Building Permit | Receive Uniform Construction Code - Building Permit | Send Letter Requesting Bond and Insurance Certificate | Received Bonds and Insurance Certificates | Write Construction Contracts | Mail Notice of Award Letter with two (2) Original Contracts | Return Bid Bonds to disappointed Bidders | School Board President executes Contracts | Return one (1) Fully executed Contract with Notice to Proceed Letter | Project Start Date | Estimated Project End Date
Task Start Date |  |  | 2009-02-23 | 2009-03-09 | 2009-03-12 | 2009-03-26 | [8 empty] | 2008-12-08 | 2008-12-16 | 2009-01-12 |  |  |  | 2009-02-04 |  | 2009-03-11 |  | 2009-03-31 | 2009-04-17
Project No. 00901 EMHS & YHS Scoreboards Purchase | N/A | N/A | 100% | 100% | 100% | PDE#: 731-09-0159-A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | N/A | 100% | 100% | 100% | N/A | N/A | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 2009-07-07 | Construction deadline: 8/14/2009
Task Start Date |  | 2009-01-12 | 2009-02-23 | 2009-03-09 | 2009-03-23 | 2009-03-26 | 2009-03-11 | 2009-03-18
Project No. 0902 WCCC Welding Shop Upgrades | Item was passed by PP&F to Board meeting. | 100% | 100% | 100% | 100% | PDE #731-09-0194-A | Work Order No. 0701.0902 w/ HRLC | 100% | [19 empty] | Construction deadline: 8/14/2009
Task Start Date | 2009-01-26 | 2009-02-09 | 2009-02-23 | 2009-03-09 | 2009-03-12 | 2009-03-26 | 2009-03-11 | 2009-03-18 | 2009-03-23 |  |  |  |  | 2009-04-30 | 2009-05-08 | 2009-04-29 | 2009-05-11 |  |  | 2009-05-12
Project No. 0903 SGES Window Replacements | 100% | 100% | 100% | 100% | 100% | PDE#: 731-09-0158-A | Work Order No. 0701.0902 w/ HRLC | 100% | 100% | 100% | 100% | 100% | 4/3/2009, 4/10/2009, 4/17/2009 | 10:00 a.m. at WCCC | 2:00 p.m. at C.O. | PP&F Committee forwards motion TBD after bid opening. | 100% |  |  | 100% | [6 empty] | 2009-09-19 | Construction deadline: 11/30/09
Task Start Date | 2009-01-26 | 2009-02-09 | 2009-02-23 | 2009-03-09 | 2009-03-12 | 2009-03-26 | 2009-05-11
Project No. 0905 SGES, SSELC & SES Fire Alarm Upgrades | 100% | 100% | 100% | 100% | 100% | PDE #: 731-09-0160-A | Work Order No. 0704.0905 w/ HF Lenz | Waiting signature by Board President. | [19 empty] | Construction deadline: 8/14/2009