## Construction Projects
WCSD Project Name & Number | PPF Forward Motion to approve work order to Architects / Engineers | Board Meeting approve work order to Architects / Engineers | Bid-Date Accept Proposals | PPF Forward Motion to approve awarding bids | Board meeting to approve awarding bids | Project Status
Project No. 1004 - SAMHS Roof Replacement | 2010-03-22 | 2010-04-12 | 2010-06-14 | 6/1/2010 - PPF passed to Board | 2010-06-14 | Completed
Project No. 1005 - YHS Boiler Replacements | 2010-04-26 | 2010-05-10 | 2010-07-23 | 2010-07-26 | 2010-07-26 | Completed
Project No. 1007 - BWMS Window Replacements | 2010-06-28 | 2010-06-28 | 2010-09-02 | 8/30/2010 - PPF passed to Board | 2010-08-13 | Project Complete
Project No. 1008 - YHS Hot Water Boiler Replacement (Emergency Job) | N/A | N/A | 2010-10-25 | 2010-10-25 | 2010-10-25 | Completed
Project No. 1101 - BWMS Driveway | 2010-09-27 | 2010-10-11 | 2011-03-10 | 2/28/2011 - PPF passed to Board | 2011-03-14 | Complete
Project No. 1102 - SAMHS Storage Building | 2010-09-27 | 2010-10-11 | 2011-01-25 | N/A - Project Re-bid as 1102R | N/A - Project Re-bid as 1102R | N/A - Project Re-bid as 1102R
Project No. 1102R - SAMHS Storage Building (Re-bid) | 2010-09-27 | 2010-10-11 | 2011-03-16 | 2011-03-28 | Project tabled at BOD meeting on 4/11/2011 | Project Cancelled
Project No. 1104 - WAHS Electrical Service Replacement (Emergency Job) | N/A | N/A | 2011-03-15 | N/A | Board approved PDE Form 3074(b) on 3/14/2011 and subsequent awarding of bids | Project Complete
Project No. 1106 - WCCC Emergency Transformer Replacement | N/A | N/A | 2011-03-21 | N/A | Board approved PDE Form 3074(b) on 9/20/2011 and subsequent awarding of bids | Complete
Project No. 1107 - EMHS Boiler Project | N/A | 2011-11-14 | 2011-12-02 | 11/21/11 - PPF passed to Board | 2011-12-05 | Project Complete

## PlanCon Projects
Project No. 1103 - BWMS Renovation (Suspended on 6/13/2011 & Reactivated on 10/10/2011) | PPF Forward Motion to approve work order to Architects / Engineers | Board Meeting approve work order to Architects / Engineers | PPF Forward Motion to approve Educational Specifications | Board Meeting to approve Educational Specifications | PPF Forward Motion to approve PlanCon A & B | Board Meeting approve/submit PlanCon A & B | Act 34 Hearing | PPF Forward Motion to approve PlanCon D | Board Meeting approve/submit PlanCon D
| N/A | 2011-01-10 | 2010-02-28 | 2011-03-14 | N/A | 2011-01-31 | N/A | 2012-02-27 | 2012-03-12
| PPF Forward Motion to approve PlanCon E | Board Meeting approve/submit PlanCon E | PPF Forward Motion to approve PlanCon F | Board Meeting to approve/submit PlanCon F | Pre-bid Meeting / Conference Date | Bid Date - Accept Proposals | PPF Forward Motion to approve awarding bids | Board meeting to approve awarding bids | Estimated Project Start Date
| 2012-02-27 | 2012-03-12 | N/A | 2012-05-21 | 2012-05-23 | 2012-06-12 | 2012-05-29 | 2012-07-23
| PPF Forward Motion to approve PlanCon G | Boarding Meeting to approve/submit PlanCon G | PPF Forward Motion to approve PlanCon H | Boarding Meeting to approve/submit PlanCon H | PPF Forward Motion to approve PlanCon I | Board Meeting to approve/submit PlanCon I | Estimated Project End Date | PPF Forward Motion to approve PlanCon J | Board Meeting to approve/submit PlanCon J
| 2012-05-29 | 2012-07-23
Project No. 1002 - EMHS Renovation (Suspended on 6/13/2011 & Reactivated on 4/23/2012) | PPF Forward Motion to approve work order to Architects / Engineers | Board Meeting approve work order to Architects / Engineers | PPF Forward Motion to approve Educational Specifications | Board Meeting to approve Educational Specifications | PPF Forward Motion to approve PlanCon A & B | Board Meeting approve/submit PlanCon A & B | Act 34 Hearing | PPF Forward Motion to approve PlanCon D | Board Meeting approve/submit PlanCon D
| 2010-03-22 | 2010-04-12 | 2012-08-30 | 2010-09-13 | 2010-09-27 | 2010-10-11 | 2012-07-23 | N/A | 2011-01-10
| PPF Forward Motion to approve PlanCon E | Board Meeting approve/submit PlanCon E | PPF Forward Motion to approve PlanCon F | Board Meeting to approve/submit PlanCon F | Pre-bid Meeting / Conference Date | Bid Date - Accept Proposals | PPF Forward Motion to approve awarding bids | Board meeting to approve awarding bids | Estimated Project Start Date
| 2011-01-31 | 2011-02-14
| PPF Forward Motion to approve PlanCon G | Boarding Meeting to approve/submit PlanCon G | PPF Forward Motion to approve PlanCon H | Boarding Meeting to approve/submit PlanCon H | PPF Forward Motion to approve PlanCon I | Board Meeting to approve/submit PlanCon I | Estimated Project End Date | PPF Forward Motion to approve PlanCon J | Board Meeting to approve/submit PlanCon J
Project No. 1203 - EMHS Elementary Addition | PPF Forward Motion to approve work order to Architects / Engineers | Board Meeting approve work order to Architects / Engineers | PPF Forward Motion to approve Educational Specifications | Board Meeting to approve Educational Specifications | PPF Forward Motion to approve PlanCon A & B | Board Meeting approve/submit PlanCon A & B | Act 34 Hearing | PPF Forward Motion to approve PlanCon D | Board Meeting approve/submit PlanCon D
| 2012-04-30 | 2012-05-14 | 2012-06-25 | 2012-06-28 | N/A (Combined with EMHS 1002 with PDE approval) | N/A (Combined with EMHS 1002 with PDE approval) | 2012-07-23 | N/A (Combined with EMHS 1002 with PDE approval) | N/A (Combined with EMHS 1002 with PDE approval)
| PPF Forward Motion to approve PlanCon E | Board Meeting approve/submit PlanCon E | PPF Forward Motion to approve PlanCon F | Board Meeting to approve/submit PlanCon F | Pre-bid Meeting / Conference Date | Bid Date - Accept Proposals | PPF Forward Motion to approve awarding bids | Board meeting to approve awarding bids | Estimated Project Start Date
| N/A (Combined with EMHS 1002 with PDE approval) | N/A (Combined with EMHS 1002 with PDE approval)
| PPF Forward Motion to approve PlanCon G | Boarding Meeting to approve/submit PlanCon G | PPF Forward Motion to approve PlanCon H | Boarding Meeting to approve/submit PlanCon H | PPF Forward Motion to approve PlanCon I | Board Meeting to approve/submit PlanCon I | Estimated Project End Date | PPF Forward Motion to approve PlanCon J | Board Meeting to approve/submit PlanCon J
Project No. 1204 - SAMHS Elementary Addition | PPF Forward Motion to approve work order to Architects / Engineers | Board Meeting approve work order to Architects / Engineers | PPF Forward Motion to approve Educational Specifications | Board Meeting to approve Educational Specifications | PPF Forward Motion to approve PlanCon A & B | Board Meeting approve/submit PlanCon A & B | Act 34 Hearing | PPF Forward Motion to approve PlanCon D | Board Meeting approve/submit PlanCon D
| 2012-04-30 | 2012-05-14 | 2012-06-25 | 2012-06-28 | 2012-06-25 | 2012-06-28 | N/A
| PPF Forward Motion to approve PlanCon E | Board Meeting approve/submit PlanCon E | PPF Forward Motion to approve PlanCon F | Board Meeting to approve/submit PlanCon F | Pre-bid Meeting / Conference Date | Bid Date - Accept Proposals | PPF Forward Motion to approve awarding bids | Board meeting to approve awarding bids | Estimated Project Start Date
| PPF Forward Motion to approve PlanCon G | Boarding Meeting to approve/submit PlanCon G | PPF Forward Motion to approve PlanCon H | Boarding Meeting to approve/submit PlanCon H | PPF Forward Motion to approve PlanCon I | Board Meeting to approve/submit PlanCon I | Estimated Project End Date | PPF Forward Motion to approve PlanCon J | Board Meeting to approve/submit PlanCon J