## Sheet1
GOAL 1: By January 2011 fund and develop, and by September 2011 implement, a continuous improvement plan for academic excellence using multiple criteria (including the possiblility of individualized learning plans for every student) to evaluate and improve individual student performance, with a new emphasis on empowering the family to be a part of the process.
Strategic Action |  | Budget | Time Frame | Person | Status of Strategic Action
1. | Overall - Grades K-12
| A. Build and implement strategies for parent involvement. | TBD | 9-2010 to 1-1-11 | Dir. of Secondary & Dir. of Elem. Ed.
| B. Engage in comprehensive curriculum mapping and analysis of the gaps in curriculum. (This will be a multi-year project.) | Within Budget | 7-1-10 to 7-1-12 | Dir. of Secondary & Dir. of Elem. Ed.
| C. Implement software to house all assessment data for students to allow staff access to data to inform instruction. | Within Budget | 2011-09-01 | Dir. of Secondary, Dir. of Elem. Ed., & Dir. of Technology
| D. Create district-wide and building level data teams to provide professional development for staff and informational workshops for parents and students in using data to make educational decisions. | Within Budget | 8-1-10 through 6-30-12 | Principals
2. | Grades K-5
| A. Focus school improvement teams around a book study of Beyond the Bake Sale, a book including strategies for parent involvement. | Within Budget | 9-1-10 to 6-30-11 | Principals
| B. Develop specific strategies for parent involvement at each elementary school. | Within Budget | 2010-10-15 | Principals
3. | Grades 6-8
| A. Use advisory time as an academic counseling period at least once per week. | Within Budget
| B. Use the Career Education and Work Standards as a framework to help students create portfolios that document academic progress, and house career exploration information for students, parents, counselors, and teachers to access. | TBD | Begin 9-1-10 Plan 3-15-11 Begin 9-1-11 | Principals, Dir. of Sec. Ed., & Dir. of Technology
| C. Utilize the portfolio information to inform schedule planning and identify students in need of additional support | TBD | Plan 3-15-11 Begin 9-1-11 | Principals
4. | Grade 9-12
| A. Implement a high school advisory program to allow for regular monitoring of student progress and additional communication with parents. | TBD | Plan 3-15-11 Begin 9-1-11 | Principals
| B. Develop career pathways for students to focus in on areas of interest to be better prepared for post-secondary study and career options when leaving high school. | TBD | Plan 3-15-11 Begin 9-1-11 | Principals
| C. Adjust the scheduling process to allow for individual meetings with students and parents to guide students toward preparation for a career pathway. | Within Budget | Plan 3-15-11 Begin 9-1-11 | Principals & Guid-ance Counselors
| D. Continue to build electronic portfolios as students progress from the middle school. | Within Budget | Plan 3-15-11 Begin 9-1-11 | Principals & Guid-ance Counselors
5. | Dropout Rate Reduction
| A. Design and implement a plan to reduce the dropout rate. | Within Spec. Ed. Budget & Stimulus Funding | Plan due 7-14-10 Implement on 9-1-10 | Principals