## Sheet1
GOAL 2: By January 2011 compile a report for evaluating the existing course offerings and adequacy of available staff to deliver appropriate instruction and to include recommendations for improvement of program offerings.
Strategic Action |  | Budget | Time Frame | Person | Status of Strategic Action
1. | Oversll - Grades K-12
| A. Establish unifrom grade configurations across the Warren County School District. | Within Budget | 10-15-10 | Dir. of Elem. Ed., Spec. Ed., & Sec. Ed.
| B. Offer staff development for administrators in observation and evaluation techniques to improve the level of and the consistency of support that can be given to the educational staff. | Within Budget | Begin 8-15-10 and continue as ongoing | Dir. of Elem. Ed., Spec. Ed., & Sec. Ed.
2. | Grades K-5
| A. Analyze and evaluate class sizes. | Within Budget | Analysis 11-15-10 Rec. 1-15-11 | Dir. of Elem Ed. & Elem. Principals
| B. Implement elementary foreign language program. | Within Budget | 9-1-11 | Dir. of Elem Ed. & Elem. Principals
3. | Grades 6-8
| A. Complete Year Two of the Schools to Watch evaluation process in all four middle school programs. | Within Budget | 1-15-11 | Dir. of Secondary Ed.
| B. Create a list of recommended changes in the Middle School program to further refine and strenghten the offerings in all curricular areas. | TBD | Rec. for 2011-12 Budget: 12-15-10 | Dir. of Secondary Ed.
4. | Grade 9-12
| A. Create a list of recommended changes in each curricular area. | TBD | Rec. for 2011-12 Budget: 12-15-10 Due: 2-15-11 | Dir. of Secondary Ed.
| B. Develop a strategy to implement the elements of high school reform as it would benefit Warren County School District. | TBD | Rec. for 2011-12 Budget: 12-15-10 Due: 2-15-11 | Dir. of Secondary Ed.
| C. Devise options for physical education that meet the state standards for Warren County School District students. | TBD | 2-15-11 | Dir. of Secondary Ed.
| D. Evaluate the options offered at the Warren County Career Center based upon employability and post-secondary attendance related to the program of study. | TBD | 12-15-10 | Dir. of Sec. Ed. & Dir. of Vocational Ed.
| E. Continue to develop and expand dual enrollment opportunities. | TBD | Rec. due 1-15-11 | Dir. of Secondary Ed.
| E.1. Establish a Foundation for dual enrollment program expansion and continuation. | Within Budget | 8-15-10 | Dir. of Technology & Grants Writer