## Sheet1
Goal 3 - By January 2011, create a plan for (1) improving and supporting instructional delivery and (2) continue recruiting highly talented staff im areas of need.
Strategic Action |  |  | Budget | Time Frame | Person | Status of Strategic Action
1. |  | Improving and supporting instructional delivery
| A. Update the teacher induction plan to include an initial three-day training for all newly-hired teachers, including: |  | Within Budget | Plan due 1-15-11 | Dir. Of Sec., Elem., Spec. Ed, & Aca-demic Coaches
• Pentamation training;
• Review of PA School Code;
• Review of PA Code of Conduct for Educators;
• Review of planned instruction and state standards; and
• Overview of the discipline policy.
| B. Provide all Instructional I teachers with mandatory periodic trainings with the academic coaches: |  | Within Budget | Plan due 1-15-11 Implementation 9-1-10 | Dir. Of Sec., Elem., Spec. Ed, & Aca-demic Coaches
• All first year teachers will have quarterly meetings with the academic coaches to discuss concerns, classroom issues, and mentor meeting.
• All second year teachers will have monthly meetings with the academic coaches focused on instructional strategies.
• All third year teachers will meet with the academic coaches once each semester to support them as the teachers develop a portfolio with evidence to support their application for a Level II certificate.
| C. | Provide teachers of all content areas with professional development that will enable them to incorporate math skills in their instruction. | Within Budget | Implementation 9-1-10 | Dir. Of Sec., Elem., Spec. Ed, & Aca-demic Coaches
• Provide teachers of all content areas with professional development that will enable them to incorporate reading skills in their instruction.
• Continue to offer opportunities for teacher training in differentiated instruction as well as co-teaching and inclusion.
• Continue to offer opportunities for teacher training relevant to data analysis and data-driven instruction.
• Continue to offer opportunities for teacher training on the skills and strategies needed to integrate technology into classroom instruction.
2. | Recruiting
| A. | Representatives of the Human Resources Department will attend job fairs and recruiting opportunities at local colleges and universities. | TBD | Plan submitted to Supt. by 10-15-10 | Dir. Of Sec., Elem., Spec. Ed, & Aca-demic Coaches
| B. | The Human Resource Department will create an attention-grabbing recruitment packet and PowerPoint for perspective applicants. | Within Budget | Publication devel-oped by 11-15-10
| C. | The Human Resource Department will develop an aggressive recruitment plan for recruiting top notch teacher, support, and administrative candidates to work and live in Warren County. | TBD | Plan submitted to Supt. By 10-15-10