Warren County School District

Eisenhower MS HS

Design and Construction Schedule

Schematic Design					 August 2, 2010-October 11, 2010

District award contract for Site Survey		October 11, 2010

Submit Plancon A&B for Bd Review			October 7, 2010

Board Meeting approve Plancon A&B		October 11, 2010

Submit Plancon A&B for PDE review		October 26, 2010

District award contract for Geotechnical Study	October 27, 2010

Warren Co Approvals:

Preliminary review with code officials

Warren County Soil Conservation District

Formal submission of Site Plan to Warren Co

Site Plan Review with Authorities

Zoning Commission review

Planning Commission review

Board of Commissioners Review/Approval

Schematic Design Estimate			October 26, 2010

Board Approves Schematic Design			October 26,2010

Preliminary Design Development				October 12, 2010-November 23, 2010

Design Development submitted for estimate	November 23, 2010

Design Development Estimate			December 7, 2010

Submit Plancon Part D&E Bd review		December 9,, 2010

Board Meeting approve Plancon D&E		December 13, 2010

Board approves Design Development		December 13, 2010

Submit Plancon D & E for PDE review		December 14, 2010

PDE review telecon Plancon D&E			December 21, 2010

Pre-Final Design Development				December 14, 2010-February 7, 2011

Final Design Documents					February 21, 2011-March 21, 2011

Design Documents submitted for estimate		March 3, 2011

Design Development Estimate			March 17, 2011

Board approves Construction Documents		March 21, 2011

Submit Plancon F to PDE				March 21, 2010

PDE review/Approval plancon F			March 28, 2011

Board Vote to Solicit Bids				March 31, 2011

Advertise Bidding for Project			April 4,11,18, 25, 2011

Submit Plancon F Bd review			May 5, 2011

Board Meeting approval Plancon F			May 9,2011

Bidding/Award Contracts	April 25 2011-May 23, 2011, two weeks to award contracts

Submit bids to Bd for review			June 9, 2011

Board Meeting approve Bids and Contracts	 	June 13, 2011

Submit Plancon F Attachment C			June 14, 2011

Construction Administration 				June 27, 2010-January 2012

Board vote to submit Plancon G			June 13, 2011

Collect Plancon G08 from Prime Contr		June 17, 2011

Submit Plancon G				June 22, 2011

Record Drawings						February 2012

Life Cycle Maintenance Profile				February 2012

Final Completion						February 2012

Warranty Inspection					October 2012