## Sheet1
GOAL 5: The WCSD will finalize a Master Facilities Plan, implementation schedule and preliminary budget by June 1, 2010. (Original date of May 1, 2010 changed by motion at May 10, 2010 BOD meeting.)
Strategic Action |  | Budget | Time Frame | Person | Status of Strategic Action
1. | The Board, Board Secretary and Central Office Directors (The Management Team) develop updated district goals. | Within Budget | 2-15-10 | Superintendent, Board, Central Office Directors
2. | Administration updates the facility needs at each school with a minimum cost estimate for each school to be in compliance with the building code, and maintaining a warm, and dry building. | Within Budget | 3-1-10 | Director of Buildings & Grounds, Architect | Architect submitted the data March 1, 2010
3. | Brainstorm central attendance options for bringing Kindergarten back to Warren. | Within Budget | 3-15-10 | Director of Buildings & Grounds, Elem. Principals, Director of Elem. Education, Architect | Addition to WAEC consideration studied.
| A. Present options to Board of Education. | Within Budget | 4-12-10 |  | Presentation for Pleasant Township presented to BOD.
4. | Administration creates a variety of options for phasing in the Facilities Master Plan | Within Budget | 4-1-10 | Superintendent, Director of Buildings & Grounds | Multiple options drafted by Superintendent and Director of B&G
5. | Administration creates financial scenarios | Within Budget | 4-12-10 | Superintendent, Business Administrator, Central Office Directors | Business Manager developed options.
| A. Overlay District Goals into a 5-year budget | Within Budget
| B. Overlay each option into a 5-year budget | Within Budget
6. | The Management Team reviews and revises the options and financial scenarios for phasing in the Facilities Master Plan. | Within Budget | Option to BOD by 4-26-10 | Board, Superintendent, Central Office Directors | Public Finance Management developed multiple financial scenarios.
| A. Schedule a special Board meeting to review the options for renovation/construction projects | Within Budget
7. | Board deliberates and takes action on the entire Master Facilities Plan (establishing the parameters for the extent, priority, and funding of the construction/renovation projects) | Within Budget | 5-17-10 | Board | BOD approved Master Facilities Plan
8. | Renovation of Eisenhower Middle/Senior High School
| A. Board approves contract to DeJong-Richter for Educational Specifications for EMHS |  | 2-8-10 | Board, Director of B&G | DeJong completed Ed. Spec. for EMHS.
| B. Board approves a contract to WTW architect for design of EMHS |  | 4-12-10 | Board, Director of B&G | WTW signed contract for design and construction supervision for EMHS
| C. Board approved Ed. Specs. (as modified) for EMHS |  | 9-13-10 | Board, Director of B&G | BOD reviewed and approved Ed. Spec for EMHS with modifications
9. | Renovation of Pleasant Township Elementary School
| A. Board selects option for housing of K-1 in the Central Attendance Area |  | 5-17-10 | Board, Director of B&G
| B. Board approves contract to DeJong-Richter for Educational Specifications for PTS Renovation |  | 5-17-10 | Board, Director of B&G | In Progress
| C. Board approves contract to WTW for PTS Renovation |  | 9-13-10 | Board, Director of B&G | WTW signed contract for design and construction supervision for PTS.
10. | Renovation of Beaty Warren Middle School |  |  |  | Contingent upon QZAB funding & approval.
| A. Board approves contract to DeJong-Richter for Education Specifications for BWMS Renovations |  |  | Board, Director of B&G | In Progress
| B. Board approves contract to WTW for BWMS Renovation |  |  | Board, Director of B&G | In Progress