## Sheet1
GOAL 4: By May 1, 2010, the Warren County School District will finalize a budget and implementation plan for and embedding technology in accordance with the Technology Strategic Plan.
Strategic Action |  |  | Budget | Time Frame | Person | Status of Strategic Action
Phase One : District
A. Planning
| • | LAN / WAN / Internet | Budget is part of planning. | August 2010 to November 2010 | Technology Dept. | RFP's for WAN and Internet in finalization stages.
| • | Data Center Hardware/Software |  |  |  | Preliminary proposal received from Consulting Group. Moving forward with to receive approval for Onsite Consulting Engagement
| • | Network telephony system |  |  |  | Preliminary Discussions with vendors over VOIP systems.
| • | Disaster Recovery | Will work within parameters of capital reserve, dedicated district funds. | November 2010-January 2011 |  | See Prelininary Proposal received from Consulting Group. More Information to come once onsite Consulting Engagement is concluded
| • | APC / Generator / Power / HVAC |  | November 2010-January 2011 |  | See Prelininary Proposal received from Consulting Group. More Information to come once onsite Consulting Engagement is concluded
| • | Server room construction/location |  | November 2010-January 2011 |  | See Prelininary Proposal received from Consulting Group. More Information to come once onsite Consulting Engagement is concluded
| • | Migration |  | November 2010-January 2011 |  | More Information to come once onsite Consulting Engagement is concluded
| • | Licensing for Phase One & Two |  | November 2010 |  | See Prelininary Proposal received from Consulting Group. More Information to come once onsite Consulting Engagement is concluded
|  | Licensing for Phase Three |  |  |  | See Prelininary Proposal received from Consulting Group. More Information to come once onsite Consulting Engagement is concluded
| • | Continue to support efforts to expand broadband opportunities throughout Warren County |  | Ongoing | Amy Stewart
| • | Maintain Technology Advisory Group |  |  |  | Meeting to be scheduled to go over Preliminary Proposal from Consulting Group
B. Testing / Implementation |  |  |  | December 2010 - March 2011
| • | Migrate servers/applications
| • | Server room construction |  | December 2010
| • | Core network installation at data center |  | December 2010
| • | Phase One & Two licensing purchases |  | December 2010
| • | Physical servers installed at data center |  | January 2011
| • | APC / Generator / Power / HVAC upgrades if necessary |  | December 2010
| • | Servers to production (1/11 - 6/11) |  | March 2011
| • | WAN / Internet (7/11) |  | July 1, 2011
C. Migraton to New User Environment |  |  |  | January 2011- March 2011
| • | Applications on-line and utilized |  | February 2011
Phase Two: Classroom / Building
A. Building Network
| • | Install network upgrades for telephony and wireless | Budget is part of planning. | Begin 11/11 through 11/12 School Year | Technology Dept.
| • | Outfit 9-12 core area classrooms with SMART boards / projectors |  |  | Tech. Dept. & B&G
| • | Outfit 9-12 teachers with portable computing devices |  |  | Tech. Dept. & B&G
| • | Plan structured teacher professional development linked to ISTE Standards | Will work within parameters of capital reserve, dedicated district funds. |  | Amy Stewart
| • | Implement structured teacher professional development linked to ISTE Standards |  |  | Amy Stewart
| • | Expand cyber/blended offereings by creating a portal environment for WCSD teachers to provide offerings to WCSD students |  |  | Amy Stewart & Tech. Dept.
| • | Increase utilization of mobile distance learning units in the classroom to expand classroom walls |  |  | Amy Stewart & Tech. Dept.
| • | Develop/Select Technology Skills Assessment |  |  | Amy Stewart
| • | Expand use of technology to enhance / improve communication between home / school |  |  | Amy Stewart & Tech. Dept.
Phase Three : Student
| • | Prepare for individual student computing devices by continuing to evaluate means of delivery |  |  | Amy Stewart & Tech. Dept.
| • | Incorporate 21st century technology systems in district building project |  |  | Tech. Dept. & B&G
| • | Purchase Phase Three Licensing |  |  | Technology Dept.