## Sheet1
GOAL 4: By May 1, 2010, the Warren County School District will finalize a budget and implementation plan for and embedding technology in accordance with the Technology Strategic Plan.
Strategic Action |  |  | Budget | Time Frame | Person | Status of Strategic Action
Phase One : District
A. Planning
| • | LAN / WAN / Internet |  | Service to Start July 1, 2011 | Technology Dept. | Board Approval - January 10, 2011
| • | Data Center Hardware/Software |  |  | Technology Dept. | Board Approval - January 10, 2011
| • | Network telephony system |  | November 2011 | Technology Dept. | Preliminary Discussions with vendors over VOIP systems.
| • | Disaster Recovery |  | Complete | Technology Dept. | Board Approval - January 10, 2011
| • | APC / Generator / Power / HVAC |  | Complete | Technology Dept. | Board Approval - January 10, 2011
| • | Server room construction/location |  | Complete | Technology Dept. | Board Approval - January 10, 2011
| • | Migration |  | Complete | Technology Dept. | Board Approval - January 10, 2011
| • | Licensing for Citrix, Gaggle.net |  | Complete | Technology Dept. | Board Approval- January 10, 2011
|  | Microsoft Licensing |  | Complete | Technology Dept. | Board Approval - March 14. 2011
|  | Licensing for Phase Three |  | 2011-2012 | Technology Dept. | Preparing for budgeting process for school year 2011-2012
| • | Continue to support efforts to expand broadband opportunities throughout Warren County |  | Ongoing | Amy Stewart
| • | Maintain Technology Advisory Group
B. Testing / Implementation
| • | Migrate servers/applications |  | May -June 2011 | Technology Dept./AEC Group
| • | Server room construction |  | May 3, 2011 | Technology Dept./AEC Group | New data center is currently operating simeltaneously with the old data center. Electrical construction is complete.
| • | Core 'Wide Area Network' equipment |  | June- September 2011 | Technology Dept./AEC Group/Zito Media Communications | District will be purchasing a core router, in addition to proposed upgrades from AEC Group, based on Zito Media Communications requirements. Quotes anticipated over the summer. Replacement once existing warranty expires.
| • | Core network installation at data center |  | May 3, 2011 | Technology Dept./AEC Group | New network core has been installed.
| • | Phase One licensing purchases |  | March 14, 2011 | Technology/GovConnection | Complete- Board Approval January 10, 2011 & March 14, 2011
| • | Physical servers installed at data center |  | May 3, 2011 | Technology Dept./AEC Group | New servers have been installed in temporary location, preparing for migration.
| • | APC / Generator / Power / HVAC upgrades if necessary |  | April 11- April 15, 2011 | Technology Dept./AEC Group | Battery Backup infrastructure being replaced- current A/C systems will remain in place
| • | Servers to production |  | May - June 2011 | Technology Dept./AEC Group
|  | Gaggle.net |  | April - May 2011 | Technology Dept./Gaggle.net | Initial setup and data migration has begun- Migration to new email system- Live July 1, 2011
| • | WAN / Internet (7/11) |  | Current- July 2011 | Technology Dept./B&G Dept. | Site visits and construction has begun to bring Zito Media Communication's Fiber into our buildings
C. Migraton to New User Environment |  |  |  | July 2011 | Technology Dept./ AEC Group | This migration will also encompass removal of old data center and installation of new data center into the footprint of the old equipment.
| • | Applications on-line and utilized |  | May - June 2011 | Technology Dept./ AEC Group
Phase Two: Classroom / Building
A. Building Network
| • | Install network upgrades for telephony and wireless | Budget is part of planning. | Begin 11/11 through 11/12 School Year | Technology Dept.
| • | Outfit 9-12 core area classrooms with SMART boards / projectors |  |  | Tech. Dept. & B&G
| • | Outfit 9-12 teachers with portable computing devices |  |  | Tech. Dept. & B&G
| • | Plan structured teacher professional development linked to ISTE Standards | Will work within parameters of capital reserve, dedicated district funds. |  | Amy Stewart
| • | Implement structured teacher professional development linked to ISTE Standards |  |  | Amy Stewart
| • | Expand cyber/blended offereings by creating a portal environment for WCSD teachers to provide offerings to WCSD students |  |  | Amy Stewart & Tech. Dept.
| • | Increase utilization of mobile distance learning units in the classroom to expand classroom walls |  |  | Amy Stewart & Tech. Dept.
| • | Develop/Select Technology Skills Assessment |  |  | Amy Stewart
| • | Expand use of technology to enhance / improve communication between home / school |  |  | Amy Stewart & Tech. Dept.
Phase Three : Student
| • | Prepare for individual student computing devices by continuing to evaluate means of delivery |  |  | Amy Stewart & Tech. Dept.
| • | Incorporate 21st century technology systems in district building project |  |  | Tech. Dept. & B&G
| • | Purchase Phase Three Licensing |  |  | Technology Dept.