## Sheet1
GOAL 5: The WCSD will finalize a Master Facilities Plan, implementation schedule and preliminary budget by June 1, 2010. (Original date of May 1, 2010 changed by motion at May 10, 2010 BOD meeting.)
Strategic Action |  |  | Budget | Time Frame | Person | Status of Strategic Action
1. | The Board, Board Secretary and Central Office Directors (The Management Team) develop updated district goals. |  | Within Budget | 1910-02-15 | Superintendent, Board, Central Office Directors
2. | Administration updates the facility needs at each school with a minimum cost estimate for each school to be in compliance with the building code, and maintaining a warm, and dry building. |  | Within Budget | 1910-03-01 | Director of Buildings & Grounds, Architect | Architect submitted the data March 1, 2010
3. | Brainstorm central attendance options for bringing Kindergarten back to Warren. |  | Within Budget | 1910-03-15 | Director of Buildings & Grounds, Elem. Principals, Director of Elem. Education, Architect | Addition to WAEC consideration studied.
| A. Present options to Board of Education. |  | Within Budget | 1910-04-12 |  | Presentation for Pleasant Township presented to BOD.
4. | Administration creates a variety of options for phasing in the Facilities Master Plan |  | Within Budget | 1910-04-01 | Superintendent, Director of Buildings & Grounds | Multiple options drafted by Superintendent and Director of B&G
5. | Administration creates financial scenarios |  | Within Budget | 1910-04-12 | Superintendent, Business Administrator, Central Office Directors | Business Manager developed options.
| A. Overlay District Goals into a 5-year budget |  | Within Budget
| B. Overlay each option into a 5-year budget |  | Within Budget
6. | The Management Team reviews and revises the options and financial scenarios for phasing in the Facilities Master Plan. |  | Within Budget | Option to BOD by 4/26/10 | Board, Superintendent, Central Office Directors | Public Finance Management developed multiple financial scenarios.
| A. Schedule a special Board meeting to review the options for renovation/construction projects |  | Within Budget
7. | Board deliberates and takes action on the entire Master Facilities Plan (establishing the parameters for the extent, priority, and funding of the construction/renovation projects) |  | Within Budget | 1910-05-17 | Board | BOD approved Master Facilities Plan
8. | Renovation of Eisenhower Middle/Senior High School |  |  |  |  | Approved in Master Facilities Plan
| A. Board approves contract to DeJong-Richter for Educational Specifications for EMHS |  |  | 1910-02-08 | Board, Director of B&G | DeJong completed Ed. Spec. for EMHS.
| B. Board approves a contract to WTW Architects for design of EMHS |  |  | 1910-04-12 | Board, Director of B&G | WTW signed contract for design and construction supervision for EMHS
| C. Board approved Ed. Specs. (as modified) for EMHS |  |  | 1910-09-13 | Board, Director of B&G | BOD reviewed and approved Ed. Spec for EMHS with modifications
| D. Board advances EMHS through PlanCon process |  |  |  | Board, Director of B&G | In Progress
|  | 1. Submission of PlanCon A & B |  | 2010-09-27 | Board, Director of B&G, Architect | Approved by BOD, submitted to PDE
|  | 2. Submission of PlanCon D |  | 2011-01-10 | Board, Director of B&G, Architect | Approved by BOD, submitted to PDE
|  | 3. Submission of PlanCon E |  | 2011-02-14 | Board, Director of B&G, Architect | Approved by BOD, submitted to PDE
|  | 4. Submission of PlanCon F |  |  | Board, Director of B&G, Architect
|  | 5. Submission of PlanCon G |  |  | Board, Director of B&G, Architect
|  | 6. Submission of PlanCon H |  |  | Board, Director of B&G, Architect
|  | 7. Submission of PlanCon I |  |  | Board, Director of B&G, Architect
|  | 8. Submission of PlanCon J |  |  | Board, Director of B&G, Architect
| E. QZAB funding accepted |  |  |  | Board, Director of B&G
9. | Renovation of Pleasant Township Elementary School |  |  |  |  | Approved in Master Facilities Plan
| A. Board selects option for housing of K-1 in the Central Attendance Area |  |  | 1910-05-17 | Board, Director of B&G
| B. Board approves contract to DeJong-Richter for Educational Specifications for PTS Renovation |  |  | 1910-05-17 | Board, Director of B&G | DeJong completed Ed. Spec. for PTS
| C. Board approves contract to WTW Architects for design of PTS Renovation |  |  | 1910-09-13 | Board, Director of B&G | WTW signed contract for design and construction supervision for PTS.
| D. Board approved Ed. Specs. (as modified) for PTS |  |  | 2010-11-08 | Board, Director of B&G | BOD reviewed and approved Ed. Spec. for PTS with modifications
| E. Board advances PTS through PlanCon process |  |  |  | Board, Director of B&G | In Progress
|  | 1. Submission of PlanCon A & B |  |  | Board, Director of B&G, Architect
|  | 2. Submission of PlanCon D |  |  | Board, Director of B&G, Architect
|  | 3. Submission of PlanCon E |  |  | Board, Director of B&G, Architect
|  | 4. Submission of PlanCon F |  |  | Board, Director of B&G, Architect
|  | 5. Submission of PlanCon G |  |  | Board, Director of B&G, Architect
|  | 6. Submission of PlanCon H |  |  | Board, Director of B&G, Architect
|  | 7. Submission of PlanCon I |  |  | Board, Director of B&G, Architect
|  | 8. Submission of PlanCon J |  |  | Board, Director of B&G, Architect
10. | Renovation of Beaty Warren Middle School |  |  |  |  | Contingent upon QZAB funding & approval.
| A. Board approves contract to DeJong-Richter for Education Specifications for BWMS Renovations |  |  | 2010-10-11 | Board, Director of B&G | Ed. Specs. In Progress for BWMS
| B. Board approves contract to WTW Architects for design of BWMS renovation |  |  | 2011-01-10 | Board, Director of B&G | WTW signed contract for design and construction supervision for BWMS
| C. Board approves Ed. Specs. (as modified) for BWMS |  |  | 2011-03-14 | Board, Director of B&G | BOD reviewed and approved Ed. Spec. for BWMS with modifications
| D. QZAB funding is accepted |  |  |  | Board, Director of B&G
| E. Board advances BWMS through PlanCon Process |  |  |  | Board, Director of B&G | In Progress
|  | 1. Submission of PlanCon A & B |  | 2011-01-31 | Board, Director of B&G, Architect
|  | 2. Submission of PlanCon D |  |  | Board, Director of B&G, Architect
|  | 3. Submission of PlanCon E |  |  | Board, Director of B&G, Architect
|  | 4. Submission of PlanCon F |  |  | Board, Director of B&G, Architect
|  | 5. Submission of PlanCon G |  |  | Board, Director of B&G, Architect
|  | 6. Submission of PlanCon H |  |  | Board, Director of B&G, Architect
|  | 7. Submission of PlanCon I |  |  | Board, Director of B&G, Architect
|  | 8. Submission of PlanCon J |  |  | Board, Director of B&G, Architect